## Sheet1
WORK PLAN
NAME OF WORK:-JJM KANNUR District-WSS TO KOLACHERY AND ADJOINING PANCHAYATHS
PHASE 3 COMMON GRAVITY MAIN FOR 6 PANCHAYATHS(KOLACHERY,NARATH,KUTTIYATTUR,
MAYYIL,MUNDERI,AND KOODALI) FROM WTP CHAVASSERYPARAMB TO GLSR AT PADIKKUNNU
DATE | PROGRESS IN % | DETAILS OF WORK
22.03.2022 | 0 | ISSUE OF WORK ORDER
04.04.2022 | 1 | EXECUTION OF AGREEMENT
01.05.2022 | 3 | PIPE(500mm DI K9&400mm DI K9),SPECIALS AND VALVES SUPPLYING
31.05.2023 | 7 | EARTH EXCAVATION AND PIPE LAYING OF GRAVITY MAIN
30.06.2022 | 12 | EARTH EXCAVATION AND PIPE LAYING OF GRAVITY MAIN
31.07.2022 | 20 | EARTH EXCAVATION AND PIPE LAYING OF GRAVITY MAIN
30.08.2022 | 25 | EARTH EXCAVATION AND PIPE LAYING OF GRAVITY MAIN
30.09.2022 | 30 | EARTH EXCAVATION AND PIPE LAYING OF GRAVITY MAIN
31.10.2022 | 35 | EARTH EXCAVATION AND PIPE LAYING OF GRAVITY MAIN
30.11.2022 | 40 | EARTH EXCAVATION AND PIPE LAYING OF GRAVITY MAIN
31.12.2022 | 50 | EARTH EXCAVATION AND PIPE LAYING OF GRAVITY MAIN
31.01.2023 | 60 | EARTH EXCAVATION AND PIPE LAYING OF GRAVITY MAIN
28.02.2023 | 65 | EARTH EXCAVATION AND PIPE LAYING OF GRAVITY MAIN
31.03.2023 | 70 | EARTH EXCAVATION AND PIPE LAYING OF GRAVITY MAIN
30.04.2023 | 75 | EARTH EXCAVATION AND PIPE LAYING OF GRAVITY MAIN,CONSTRUCTION OF AIR VALVE CHAMBER
31.05.2023 | 80 | EARTH EXCAVATION AND PIPE LAYING OF GRAVITY MAIN,CONSTRCTION OF AIR VALVE CHAMBER
30.06.2023 | 85 | EARTH EXCAVATION AND PIPE LAYING OF GRAVITY MAIN,CONSTRUCTION OF AIR VALVE CHAMBER
31.07.2023 | 90 | EARTH EXCAVATION AND PIPE LAYING OF GRAVITY MAIN,CONSTRUCTION OF AIR VALVE CHAMBER
30.08.2023 | 95 | TRIAL RUNNING AND COMMISSIONING OF THE PROJECT
31.09.2023 | 100 | TRIAL RUNNING AND COMMISSIONING OF THE PROJECT