## Sheet1
Work Name : | JJM-2020-2021 - Panavoor Grama Panchayat-Providing Functional Household Tap Connections and providing pipe line extensions in panavoor grama panchayath Phase 2
Work Order No: | KWA/PHC/D3/15085/2020/JJM(Panavoor)
Contractor: | Sri.Jai Associates Sanjuan ,House no 57 ,udhaya Garden Ulloor tvm
Planned
Actual
Proposed
|  |  | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01
|  |  | 2022-03-01: MAR-1-15 | MAR-16-31
1 | Receipt of Work order | Planned | bar: 2020-09-01
Actual | bar: 2020-09-01
2 | Pipe Supply | Planned | bar: 2020-10-01
Actual | bar: 2020-12-01; 2021-02-01; 2021-12-01
3 | Earth work and Pipe Laying | Planned | bar: 2020-10-01 to 2021-02-01
Actual | bar: 2020-12-01 to 2022-02-01
4 | Providing FHTCs | Planned | bar: 2020-10-01 to 2021-02-01
Actual | bar: 2021-01-01 to 2022-03-01
5 | Fixing of valves and construction of valve chamber | Planned | bar: 2021-03-01
Actual | bar: 2021-12-01 to 2022-01-01
6 | Restoration -Concrete | Planned | bar: 2020-12-01; 2021-03-01
Actual | bar: 2021-02-01; 2021-04-01; 2021-06-01; 2021-08-01; 2021-10-01; 2021-12-01