## Sheet1
WORK PLAN
NAME OF WORK:-JJM KANNUR District MALUR GP-WSS to Mattannur & Iritty
Adjoining Panchayath Phase-3 Laying Distribution system and Providing FHTCS
DATE | PROGRESS IN % | DETAILS OF WORK
08.08.2023 | 0 | ISSUE OF WORK ORDER (zone 1)
01.09.2023 | 1 | EXECUTION OF AGREEMENT (zone 1)
10.09.2023 | 2 | PIPE,SPECIALS AND VALVES SUPPLYING (zone 1)
30.09.2023 | 5 | EARTH EXCAVATION AND PIPE LAYING (zone 1)
ISSUE OF WORK ORDER OF ZONE 2 & 3
31.10.2023 | 10 | EARTH EXCAVATION AND PIPE LAYING (zone 1),Construction of 8.0LL GLSR TANK (ZONE 1)
EXECUTION OF AGREEMENT OF ZONE 2 & 3
27.11.2023 | 15 | PIPE,SPECIALS AND VALVES SUPPLYING (zone 2&3)
EARTH EXCAVATION AND PIPE LAYING (zone 1),Construction of 8.0LL GLSR TANK (ZONE 1)
07.12.2023 | 20 | EARTH EXCAVATION AND PIPE LAYING OF ZONE 2& 3
Construction of 8.0LL GLSR TANK(Zone 1) , PIPE LAYING OF Zone 1
30.12.2023 | 30 | Construction of 8.0LL GLSR (Zone 1),1.5LL OHSR PUMPING(ZONE-2) & PIPE LAYING OF (Zone 1,2&3).Providing FHTCs of zone-1
31.01.2024 | 40 | Construction of 8.0LL GLSR(Zone 1),1.5LL OHSR PUMPING(zone2) & PIPE LAYING OF (Zone1,2&3)
Providing FHTCs of zone 1.construction of .25LL BOOSTER SUMP AND 1.0LL CAPACITY OHSR ZONE 3
28.02.2024 | 50 | Construction of 8.0LL GLSR (Zone 1),1.5LL OHSR PUMPING zone 2 & PIPE LAYING OF (Zone1, 2&3)
Providing FHTCs of zone 1 & 2.Construction of 0.25LL Capacity booster sump&1.0LL OHSR ZONE 3
31.03.2024 | 60 | Construction of1.5LL OHSR ZONE2) & PIPE LAYING OF (Zone1, 2 &3 ),Construction of 8.0LL Capcity GLSR ZONE 1
PUMP SET ERRECTION ZONE 2 AND PROVIDING FHTCS OF ZONE 1 AND 2.Construction of 0.25LL SUMP&1LL OHSR ZONE 3
30.04.2024 | 70 | Construction of 8.0LL GLSR,PIPE LAYING OF ZONE 1&3.CONSTRUCTION OF 0.25LL CAPACITY SUMP&1LL PUMPING OHSR ZONE-3
Trial running of Zone-2.Providing FHTCs of zone-1 &3
31.05.2024 | 80 | Construction of 8.0LL GLSR,PIPE LAYING OF ZONE 1&3.CONSTRUCTION OF 0.25LL CAPACITY SUMP&1LL PUMPING OHSR ZONE-3
Providing FHTCs of zone 1 & 3
30.06.2024 | 85 | Construction of 0.25 LL GLSR BOOSTER,1.0LL OHSR PUMPING & PIPE LAYING OF (Zone 3).Providing FHTCs of zone 1 & 3
Construction of 8.0LL GLSR & PIPE LAYING OF ZONE 1
31.07.2024 | 90 | Pump set Errection &Trial Running of zone 1 & 3
31.08.2024 | 95 | Trial running of the scheme(Zone 1,2 & 3)
22.09.2024 | 99 | COMMISSIONING OF THE SCHEME
31.09.2024 | 100 | COMMISSIONING OF THE SCHEME