## Sheet1
Work Name : | KIIFB-KIIFB - CWSS to Kallara and Pangode Panchayaths-Replacing 300 mm AC pipeline along Nellimukku Iyyermukku(Thannichal) road with 300 mm DI K9 pipe and Replacing 125 mm AC pipe near Paluvalli and Vattakkarikkakom with 140 mm PVC 10 Kg/cm2 pipe. (Project-5) -General Civil Work
Work Order No: | r e-Tender No WRD/KWA-CE(SR)/TR/8403/2022_5_1_1/1 dated 10-07-2023
Contractor: | Sri/Smt M/s.S.ANILKUMAR PAN : ACKPT4609C
Planned
Actual
Proposed
|  |  | july | auyg | sep | oct | nov | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01
1 | Receipt of Work order | Planned
Actual
2 | Pipe Supply | Planned
Actual
3 | pipe laying work | Planned
Actual
4 | valve chamber work | Planned
Actual
| completion of project | Planned
Actual

## Sheet2
Work Name : | JJM-2020-2021 - Pullampara Grama Panchayat-Providing Functional Household Tap Connections and providing pipe line extensions in Pullampara grama panchayath Phase 2
Work Order No: | KWA/PHC/D3/15090/2020/JJM(Pullampara)
Contractor: | Sri.Sreekumar S ,Aswathy ,paloorkonam ,parasala PO
Planned
Actual
Proposed
|  |  | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01
|  |  | 2022-03-01: MAR 1-15 | MAR 11-31
1 | Receipt of Work order | Planned | bar: 2020-10-01
Actual | bar: 2020-10-01
2 | Pipe Supply | Planned | bar: 2020-11-01
Actual | bar: 2020-11-01; 2021-12-01
3 | Earth work and Pipe Laying | Planned | bar: 2020-10-01 to 2021-02-01
Actual | bar: 2020-12-01 to 2021-04-01; 2021-12-01 to 2022-02-01
4 | Providing FHTCs | Planned | bar: 2020-10-01 to 2021-02-01
Actual | bar: 2020-12-01 to 2021-04-01; 2021-12-01 to 2022-03-01
5 | Fixing of valves and construction of valve chamber | Planned | bar: 2021-03-01
Actual
6 | Restoration -Concrete | Planned | bar: 2020-12-01; 2021-03-01
Actual | bar: 2021-02-01 to 2021-04-01; 2022-02-01