## Лист1
Deposit work- 2020-21- Angamaly Block Panchayath - Project No. 14520-Providing water supply connections for 14 nos families at Tharanilam Colony in Kanjoor Panchayath .
ID | Task name | Duration | Start | Finish | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01
1 | Documentation | 90 | 2022-01-17 | 2022-04-16
2 | Procurment of pipe | 14 | 2022-01-17 | 2022-01-31
3 | Providing FHTC | 67 | 2022-02-01 | 2022-04-16