## plan
Sl No | Item
1 | CWSS to Ettumanoor and adjoining villages in Kottayam District – Supply, erection, testing and commissioning 400 KVA outdoor transformer and allied works at treatment plant site Gandhinagar-11 KV Equipments -Supply and erection of all materials and providing 11 KV sub station yard using 4 No 175x85mm ISMB joist of 9.5m height, 100x50mm,height 100x500, MS channel cross arms. 2 sets of 200 A, 11 KV gang operated AB swithches with operating handles of required length 2 sets of 11 KV DO fuses,Pin insulators, Disc insulators and inter connections of the above items using 8mm dia copper wire with proper copper sockets, including all associateds civil works and painting of all structures with two coats of Zinchromate primer and aluminium paint etc. complete as per standard construction practices approved by Kerala Electrical inspectorate and relevant standards | Planned
Actual
2 | 15.59 Supply and erection of all materials and providing substation yard fencing using 50x50x6mm angle iron frame work of size 1500x2500mm fitted with weld mesh of 10 guage and bolted the same to 100x50x6mm vertical channel erected at 1500mm c/c and 2500mm above ground level of substation yard and 500 mm below with 300x300mm plain cement concrete (1:3:6) base using 40 mm granite aggregate and top surface finished neat and including all structurers with two coats of zinchromate primer and aluminium paint etc. complete as per standard construction practices approved by Kerala Electrical Inspectorate and relevant standards. | Planned
Actual
3 | Supply and erection of all materials and providing 2000mm wide 2500mm height weld mesh gate made out of 50x50x6mm Angles with necessary foundation locking relevant standards arragements etc. complete, including painting with two coats of zinchromate primer and alumunium paint as per standards | Planned
Actual
4 | Transformer-Supply, erection, testing and commissioning of 400 KVA, 11 KV/433V,50HZ, 3 Phase ONAN outdoor type copper wound distribution transformers with HV and LV side cable end box arrangements, off load tap changer with 5 tap positions have +5% to 5% variations in 2.5% steps with first filling of oil etc. complete with all fittings as per oil etc. complete with all fittings as per IS 2026 and Kerala Electrical Inspectorate Standards | Planned
Actual
5 | TOD Meter-Supply, errection, testing and commissioning of 3 phase 4 wire,0.2s Cl,-/5A TOD meter with maximum demanding in KVA suitable for the above out door metering set housed in a weather proof out door kosk.<br>The rate shall include the cost of testing the equipments at K.S.E.B and all other incidental expenses. | Planned
Actual
6 | 11KV Metering unit-Supply, erection, testing and commissioning of outdoor type metring unit consisting of the following accessiories current transformer. <br>CT ratio 15/5A<br>Burden- 10VA<br>Accuracy class0.2s<br>Potential transformer<br>PT ratio-11KV/110V<br>Burden - 25 VA<br>Accuracy class0.2s<br>The rate shall include the cost of testing the equipment at KCV and all other incidental expenses. The CT ratio should be fixed only after obtain the power allocation from K.S.E.B." | Planned
Actual
7 | Lighting Distribution board (LDB)<br>Supply, erection, testing commissioning of MCB distribution board comprising to the following .<br>32A TPN 4 pole MCB 1 No as incomer with 32A30.<br>6/10A SP MCB18 Nos. as outgoings. With tinned copper busbars/cables.,interconnection, housed in a suitable metal enclosure as per KE1 nstandards fixed in open system. | Planned
Actual
8 | Lighting Switch board (LSB)<br><br>200A TPN bus bars of sizes Phase. <br>Phase: 50x6mm Alflat.<br>Neutral: 50x6mm Al-flat.<br>Earting conductor: 25x3mm copper<br> 200A TPN Isolator 1 No. as incomer, Metering, comparments, comprising of Voltmeter, ammeter, selector switches, indicating lamps etc. complete as per KEI standards. | Planned
Actual
9 | Design, engineering, supply erection testing and commissioning of medium voltage sheet steel clad, totally ;enclosed, dust tight & vermin proof, indoor floor mounted cubicle type switchboard fabricated out of 1.4 swg mild steel sheet, and bus duct of high conductivity alumunium bus bars, pvc sleeved, air insulated and of adequate sixe as mentioned below, for operation on 3 phase, 4 wire, 415 volts, 50 Hz. Ac supply system. The ACBs switch fuse units all materials and relays etc. should be reputed make and confirming IS specification and are assembled and interconnected, earthed and the switch board shold be painted with anti-rust primer coating followed by two coats of paint of approved shade as per standrd construction pratices approved by Kerala Electrical Inspectorate and relevant standards.-Main Switch board(MSB)<br>800A TPN bus bars of sizes<br>Phase:2x50x10mm Al-flat<br>Neutral: 1x50x10mm Alflat<br>Earting conductor: 25x3mm copper<br>800A,25MVA,4 pole, ACB with all protctive devises two. <br>400A TPN SFUs 3 Nos as outgoings.<br>250A TPN SFUs 3 Nos as outgoings.<br> Metering compartments comprising of Voltmeters, ammeters, power factor meters, selector, switches, CDG-11 of equivalent relays, energy meters for all outgoing feeders, indicating lamps etc complete as per KEI standrads. | Planned
Actual
10 | Cabling-Supply and erection of all materials and providing end termination of the following size PVC/XLPE insulated, sheathed armoured Aluminium conductor cable (1100 volts grade) for giving power connections to Transformers, Panel boards etc. complete as per standrards. | Planned
Actual
11 | Cabling-Supply, erection, laying, testing and commissioning of the following size PVC/XLPE insulated sheathed armoursed Aluminium conductor cable (1100 volts grade) clamped on wall/celling with clamps and saddle clips patly laid in cable tray/partly laid in trench. | Planned
Actual
12 | 100.60.1.3.2 Providing 20mm (3/4 inch) house connection with 15mm (1/2 inch) water meter from existing PVC / HDPE mains up to 110 mm dia., up to a length of 5 m using 25mm Indian Standard Class 6 uPVC pipe and uPVC / GM / Brass specials viz. brass ferrule, GM full way wheel valve, Elbow, MTA, FTA, couplers, PVC Service Saddle of suitable size etc. and connecting with the mains, testing the joints etc. complete including trenching and refilling in all kinds of soil up to a depth of 1.50m for main line tracing and trench of average cross section 0.3m x 0.75m for laying connection pipe and service pipe, fixing water meter, lighting, watching, providing caution boards, traffic control etc. complete including cost of materials, hire for tools, cost of consumables and labour charges, including the cost of tested Class B Multijet water meter with ISI mark and weather resistant PP / PE meter box of minimum size 300mm x 200mm x 150mm, but excluding charges for cutting the concrete / tarred / bituminous roads etc, and as per the direction of the departmental officers. | Planned
Actual
13 | Earthing-Supplying and fixing of MS angle cable tray for clamping the various sizes of cables in trenches through walls and trusses etc. Angles and plates should be painted with one coat of primer and 2 coats of enamel paint as required as per KEI standards. | Planned
Actual
14 | Earthing-Supply, laying and termination of the following sizes of copper strip wires for earthing of substation, transformers. LT panel boards, equipments and inter connection of earth pits etc. | Planned
Actual
15 | Earthing-Supply of all materials and providing pipe earthing using 38mm dia performated GI pipe buried in ground at a depth of 3.0m from ground level with alternate layers of charcoal and salt including supply& fixing of tunnel for watering purpose, copper strips including construction of masonarythrough with MS cover as per IS 3043-1987 | Planned
Actual
16 | EARTHING-Supply and erection of all materials and providing plate earthing using 1200mmx1200mmx12.5mm size cast iron earth plate burries in ground at a depth of 3.0 m from ground level with alternative layers of charcoal and salt including supply & fixing of 38 mm dia perforated GI pipe funnel for watering purpose, copper, strips including construction of masonty through with MS cover as per IS 3043-1987 | Planned
Actual
17 | Safety items-Supply and providing the following safety items approved by Kerala Electrical inspectorate and relevant standards | Planned
Actual
18 | for changing over assembly to our new transformer to exisiting tranformer | Planned
Actual
19 | Preparation of drawing, submission and getting approval from electrical Inspectorate | Planned
Actual

## bill summary
[6 empty] | Ist | 2nd | 3rd | 4th | 5th | 6th | 7th
|  |  |  | 56,29,00,000 |  | 2019-03-01 | 2019-05-09 | 2019-08-27 | 2019-12-11 | 2020-02-11 | 2020-06-22 | 2020-10-12
Sl No |  |  |  | Item | Acc | [7 empty] | This bill | Final
I |  |  |  | Design approval charges | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0 | 0 | 0
II |  |  |  | WTP | [8 empty] | 0 | 0 | 0
| A |  |  | Construction of Aerator | [8 empty] | 0 | 0 | 0
|  | 1 |  | EW excavation & RCC Civil work | 0.34 | 0.17 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0 | 0 | 0
|  | 2 |  | Plastering & Finishing | 0.14 |  |  |  | 0.14 | 0.14 | 0.14 | 0.14 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
| B |  |  | Construction of RW Channel | [8 empty] | 0 | 0 | 0
|  | 1 |  | EW excavation & RCC Civil work | 0.33 | 0.165 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0 | 0 | 0
|  | 2 |  | Plastering & Finishing | 0.07 |  |  | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
| C |  |  | Construction of Flash Mixer | [8 empty] | 0 | 0 | 0
|  | 1 |  | EW excavation & PCC | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0 | 0 | 0
|  | 2 |  | RCC Civil work | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0 | 0 | 0
|  | 3 |  | Plastering & Finishing | 0.1 |  |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
| D |  |  | Chemical house | [8 empty] | 0 | 0 | 0
|  | 1 |  | EW excavation & PCC | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0
|  | 2 |  | RCC coulmn upto Plinth and Flooor concrete | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0 | 0 | 0
|  | 3 |  | RCC upto GF | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 0 | 0 | 0
|  | 4 |  | RCC upto FF | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0 | 0 | 0
|  | 5 |  | Brick work/ Solid block work | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0 | 0 | 0
|  | 6 |  | Plastering | 0.13 | 0.065 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0 | 0 | 0
|  | 7 |  | AL door, window, Painting & other finishing | 0.26 |  |  |  | 0.1 | 0.065 | 0.1 | 0.26 | 0.16 | 0 | Window glass & Painting pending
[13 empty] | 0 | 0 | 0
| E |  |  | Alum Lime Tank | 1.18 | 1.18 | 1.18 | 1.18 | 1.18 | 1.18 | 1.18 | 1.18 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
| F |  |  | Chlorine Room | [8 empty] | 0 | 0 | 0
|  | 1 |  | EW excavation & Foundation upto Plinth | 0.04 |  |  | 0.02 | 0.04 | 0.04 | 0.04 | 0.04 | 0 | 0 | 0
|  | 2 |  | Brick work/ Solid block work | 0.02 |  |  |  |  | 0.02 | 0.02 | 0.02 | 0 | 0
|  | 3 |  | RCC work | 0.27 |  |  |  | 0.27 | 0.27 | 0.27 | 0.27 | 0 | 0 | "
|  | 4 |  | Plastering, door, window, Painting & other finishing | 0.11 | [5 empty] | 0.055 | 0.11 | 0.055 | 0 | Plastering completed Window Glass pending
[13 empty] | 0 | 0 | 0
| G |  |  | Office Bldg with toilet | [8 empty] | 0 | 0 | 0
|  | 1 |  | EW excavation & Foundation upto Plinth | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0
|  | 2 |  | Brick work/ Solid block work | 0.2 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0
|  | 3 |  | RCC work | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0 | 0 | 0
|  | 4 |  | Plastering, door, window, Painting & other finishing | 0.15 |  | 0.075 | 0.075 | 0.075 | 0.075 | 0.075 | 0.15 | 0.075 | 0 | Window glass & Painting pending
[13 empty] | 0 | 0 | 0
| H |  |  | Flocculator | [8 empty] | 0 | 0 | 0
|  | 1 |  | EW excavation | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0 | 0 | 0
|  | 2 |  | Mat Concreting | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0 | 0 | 0
|  | 3 |  | RCC Floor Slab | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 0 | 0 | 0
|  | 4 |  | RCC Haunch & side wall of Flocculator - 1st lift | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0
|  | 5 |  | RCC sidewall - 2nd lift | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0
|  | 6 |  | RCC sidewall - 3rd lift | 0.9 | 0.45 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0
|  | 7 |  | Plastering & Finishing | 1.4 |  |  | 1.4 | 1.4 | 1.4 | 1.4 | 1.4 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
| I |  |  | Clarifier | [8 empty] | 0 | 0 | 0
|  | 1 |  | EW excavation | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0 | 0 | 0
|  | 2 |  | Mat Concreting | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0 | 0 | 0
|  | 3 |  | RCC Floor Slab | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 0 | 0 | 0
|  | 4 |  | RCC Haunch & side wall of Clarifier - 1st lift | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0
|  | 5 |  | RCC sidewall - 2nd lift | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0
|  | 6 |  | RCC sidewall - 3rd lift | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0
|  | 7 |  | Plastering & Finishing | 1.4 |  | 0.35 | 0.35 | 1.3 | 1.4 | 1.4 | 1.4 | 0 | 0 | 0.1
|  | 8 |  | SS plate for plate settler | 0.69 |  |  |  | 0.345 | 0.69 | 0.69 | 0.69 | 0 | 0
[13 empty] | 0 | 0 | 0
| J |  |  | Clarified Water Channel | [8 empty] | 0 | 0 | 0
|  | 1 |  | EW excavation and mat concrete | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0 | 0 | 0
|  | 2 |  | RCC work for floor slab, sidewall & cover slab | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0
|  | 3 |  | Plastering | 0.02 |  | 0 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0
| K |  |  | CW P/H & Filter house | [8 empty] | 0 | 0 | 0
|  | 1 |  | EW excavation | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
|  | 2 |  | CC for Mat foundation | 0.6 |  | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0 | 0 | 0
|  | 3 |  | RCC Floor Slab | 1.7 |  | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 0 | 0 | 0
|  | 4 |  | RCC for footings & column 1st lift | 1.5 |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0
|  | 5 |  | RCC for column - 2nd lift | 0.25 |  | 0.125 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0
|  | 6 |  | RCC for column - 3rd lift | 0.25 |  | 0.125 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0
|  | 7 |  | Side wall - 1st lift | 1 |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
|  | 8 |  | Side wall - 2nd lift | 1 |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
|  | 9 |  | Side wall - 3rd lift | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
|  | 10 |  | RCC slab for pipe gallery level | 1.08 |  |  | 1.08 | 1.08 | 1.08 | 1.08 | 1.08 | 0 | 0 | 0
|  | 11 |  | RCC construction side and manifold | 0.95 |  |  | 0.7 | 0.95 | 0.95 | 0.95 | 0.95 | 0 | 0 | 0
|  | 12 |  | RCC for beams & cover slab | 2.5 |  |  | 1.25 | 2.5 | 2.5 | 2.5 | 2.5 | 0 | 0 | 0
|  | 13 |  | Columns inside filter - 1st lift | 0.1 |  |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0
|  | 14 |  | Columns inside filter - 2nd lift | 0.1 |  |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0
|  | 15 |  | Columns inside filter - 3rd lift | 0.1 |  |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0
|  | 16 |  | RCC sidewall of filter house - 1st lift | 1.3 |  |  | 0.325 | 1.3 | 1.3 | 1.3 | 1.3 | 0 | 0 | 0
|  | 17 |  | RCC sidewall of filter house - 2nd lift | 1.3 |  |  | 0.325 | 1.3 | 1.3 | 1.3 | 1.3 | 0 | 0 | 0
|  | 18 |  | RCC sidewall of filter house - 3rd lift | 1.3 |  |  | 0.25 | 1.3 | 1.3 | 1.3 | 1.3 | 0 | 0 | 0
|  | 19 |  | Slab | 1 |  |  |  | 0.75 | 1 | 1 | 1 | 0 | 0
|  | 20 |  | Brick work/ Solid block work | 0.15 |  |  |  | 0.15 | 0.15 | 0.15 | 0.15 | 0 | 0 | 0
|  | 21 |  | Column upto floor slab of WW tank | 0.75 |  |  |  |  | 0.75 | 0.75 | 0.75 | 0 | 0
|  | 22 |  | RCC beams and balance wash water tank | 0.1 |  |  |  |  | 0.1 | 0.1 | 0.1 | 0 | 0 | "
|  | 23 |  | Plastering | 0.81 |  |  |  | 0.2 | 0.405 | 0.81 | 0.81 | 0 | 0 | Completed
|  | 24 |  | Painting, providing doors and windows | 0.28 |  |  |  |  | 0.07 | 0.14 | 0.28 | 0.14 | 0 | 50% Painting and Window glass pending
|  | 25 |  | Floorings | 1.55 |  |  |  |  | 0.775 | 1.55 | 1.55 | 0 | 0 | Completed
|  | 26 |  | Cost of Filter media | 2.46 |  |  |  |  | 0.49 | 0.615 | 2.46 | 1.845 | 0 | 50%
[13 empty] | 0 | 0 | 0
| L |  |  | Wash Water Tank | [8 empty] | 0 | 0 | 0
|  | 1 |  | Floorslab of WW Tank | 0.19 |  |  |  |  | 0.19 | 0.19 | 0.19 | 0 | 0 | Completed
|  | 2 |  | RCC for sidewall | 0.24 |  |  |  |  | 0.24 | 0.24 | 0.24 | 0 | 0 | "
|  | 3 |  | RCC for roof slab | 0.14 |  |  |  |  | 0.14 | 0.14 | 0.14 | 0 | 0 | "
|  | 4 |  | Plastering & Finishing | 0.17 | [5 empty] | 0.17 | 0.17 | 0 | 0 | Completed
[13 empty] | 0 | 0 | 0
| M |  |  | Clear Water Channel | [8 empty] | 0 | 0 | 0
|  | 1 |  | EW excavation | 0.02 |  |  |  | 0.02 | 0.02 | 0.02 | 0.02 | 0 | 0 | 0
|  | 2 |  | CC for Mat foundation & floor slab | 0.12 |  |  |  | 0.06 | 0.09 | 0.12 | 0.12 | 0 | 0 | Completed
|  | 3 |  | RCC for sidewall and cover slab | 0.14 |  |  |  |  | 0.07 | 0.14 | 0.14 | 0 | 0 | Completed
|  | 4 |  | Plastering & Finishing | 0.03 | [5 empty] | 0.03 | 0.03 | 0 | 0 | Completed
|  | 5 |  | Installation of flow meter | 0.06 | [7 empty] | 0 | 0.06 | 0
[13 empty] | 0 | 0 | 0
| N |  |  | Clear Water PH | [8 empty] | 0 | 0 | 0
|  | 1 |  | RCC for column | 0.2 |  | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0
|  | 2 |  | Brick work/ Solid block work | 0.07 |  |  | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0 | 0 | 0
|  | 3 |  | RCC for lintel beams | 0.55 |  |  | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0 | 0 | 0
|  | 4 |  | RCC for roof slab, beams etc | 0.47 |  |  |  | 0.47 | 0.47 | 0.47 | 0.47 | 0 | 0 | 0
|  | 5 |  | Plastering & other finishing works inc doors & windows | 0.2 |  |  |  | 0.1 | 0.1 | 0.1 | 0.2 | 0.1 | 0 | 50%
|  | 6 |  | Supplying & fixing gantry crane | 0.08 |  |  |  |  | 0.08 | 0.08 | 0.08 | 0 | 0 | Completed
[13 empty] | 0 | 0 | 0
| O |  |  | WW line to recycling unit | [8 empty] | 0 | 0 | 0
|  |  |  | channel to Recycling unit | 1.33 |  |  | 0.52 | 0.52 | 0.665 | 1 | 1 | 0 | 0.33 | 90%
[13 empty] | 0 | 0 | 0
| P |  |  | Mechanical works | [8 empty] | 0 | 0 | 0
|  | 1 |  | Aerator piping | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0 | 0 | 0
|  | 2 |  | Air Blower | 0.16 |  |  |  |  | 0.12 | 0.16 | 0.16 | 0 | 0 | Completed
|  | 3 |  | Flow meter, dial guages | 0.16 | [6 empty] | 0.08 | 0.08 | 0.08 | 0
|  | 4 |  | Flash mixer, agitator, motor unit | 0.24 |  |  |  | 0.12 | 0.18 | 0.24 | 0.24 | 0 | 0 | Completed
|  | 5 |  | Clarifier & Flocculator | [8 empty] | 0 | 0 | 0
|  |  | a | Bridge | 1.59 |  |  | 0.95 | 0.95 | 1.59 | 1.59 | 1.59 | 0 | 0
|  |  | b | Pipe & Fitting | 0.13 |  |  |  |  | 0.13 | 0.13 | 0.13 | 0 | 0 | 0.13
|  |  | c | Floculator motor reduction gear and bearing for agitator | 0.56 |  |  |  | 0.28 | 0.56 | 0.56 | 0.56 | 0 | 0 | Completed
|  |  | d | Motor reduction gear and agitating system | 0.4 |  |  |  | 0.2 | 0.4 | 0.4 | 0.4 | 0 | 0 | Completed
|  | 6 | a | Clorine room - cylinder & accessories | 0.4 | [6 empty] | 0.2 | 0.2 | 0.2 | 0
|  | 7 | a | Clear water Sump - CI pipe and fitting | 0.16 |  |  |  |  | 0.08 | 0.16 | 0.16 | 0 | 0 | Completed
|  | 8 |  | Filter House | [8 empty] | 0 | 0 | 0
|  |  | a | PVC laterals | 0.13 |  |  |  |  | 0.065 | 0.13 | 0.13 | 0 | 0 | Completed
|  |  | b | CI pipe and fittings (pipe gallery) | 0.24 |  |  |  | 0.12 | 0.18 | 0.24 | 0.24 | 0 | 0 | Completed
|  |  | c | CI valves & fittings | 0.52 |  |  | 0.26 | 0.26 | 0.39 | 0.52 | 0.52 | 0 | 0 | Completed
|  |  | d | WW pipe & fittings & pump | 0.4 |  |  |  |  | 0.1 | 0.4 | 0.4 | 0 | 0 | Completed
|  | 9 |  | Setting up lab, Lab equipments, safety equipments & furniture | 0.3 | [7 empty] | 0 | 0.3 | 0
|  | 10 |  | Electrical fittings and electrification | 0.56 | [6 empty] | 0.28 | 0.28 | 0.28 | 50%
[13 empty] | 0 | 0 | 0
III |  |  |  | SUB Station | [8 empty] | 0 | 0 | 0
|  | 1 |  | Site clearance & EW excavation | 0.12 |  |  |  | 0.12 | 0.12 | 0.12 | 0.12 | 0 | 0 | 0
|  | 2 |  | PCC & Column upto plinth level | 0.13 |  |  |  | 0.13 | 0.13 | 0.13 | 0.13 | 0 | 0 | 0
|  | 3 |  | RCC column upto 1st floor level | 0.09 |  |  |  | 0.09 | 0.09 | 0.09 | 0.09 | 0 | 0 | 0
|  | 4 |  | On completion of tie beam, lintel roof beam | 0.12 |  |  |  | 0.06 | 0.12 | 0.12 | 0.12 | 0 | 0
|  | 5 |  | On completion of roof slab | 0.16 |  |  |  |  | 0.16 | 0.16 | 0.16 | 0 | 0 | "
|  | 6 |  | Brick work / Solid block work | 0.14 |  |  |  | 0.14 | 0.14 | 0.14 | 0.14 | 0 | 0 | "
|  | 7 |  | Fixing door & windows | 0.06 | [6 empty] | 0.06 | 0.06 | 0 | Completed
|  | 8 |  | Plastering, painting & tiling | 0.13 |  |  |  |  | 0.065 | 0.065 | 0.13 | 0.065 | 0 | 90%
|  | 9 |  | Electrical works | 0.2 | [6 empty] | 0.1 | 0.1 | 0.1 | 50%
[13 empty] | 0 | 0 | 0
IV |  |  |  | Conctruction of BPT | [8 empty] | 0 | 0 | 0
|  | 1 |  | EW excavation | 0.01 |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0 | 0 | 0
|  | 2 |  | Foundation & mat concreting | 0.52 |  |  | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0 | 0 | 0
|  | 3 |  | RCC sidewall upto Level 1 | 0.17 |  |  | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0 | 0 | 0
|  | 4 |  | RCC roof slab - level -1 | 0.02 |  |  |  | 0.02 | 0.02 | 0.02 | 0.02 | 0 | 0 | 0
|  | 5 |  | RCC sidewall upto Level 2 | 0.15 |  |  |  | 0.15 | 0.15 | 0.15 | 0.15 | 0 | 0 | 0
|  | 6 |  | RCC roof slab - level -2 | 0.02 |  |  |  | 0.02 | 0.02 | 0.02 | 0.02 | 0 | 0 | 0
|  | 7 |  | RCC sidewall upto Level 3 | 0.19 |  |  |  |  | 0.1425 | 0.19 | 0.19 | 0 | 0 | Completed
|  | 8 |  | RCC roof slab - level -3 | 0.02 | [5 empty] | 0.02 | 0.02 | 0 | 0 | "
|  | 9 |  | Plastering | 0.11 | [5 empty] | 0.11 | 0.11 | 0 | 0 | "
|  | 10 |  | Providing hand rails, lighteing arrestor | 0.06 | [6 empty] | 0.06 | 0.06 | 0 | 50%
|  | 11 |  | Providing pipe fittings, valve chamber, valves | 0.13 |  |  |  |  | 0.0325 | 0.0325 | 0.065 | 0.0325 | 0.065 | 50%
[13 empty] | 0 | 0 | 0
V |  |  |  | Compound Wall & Fencing | 0.4 | 0.08 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.1 | 0.1 | 75%
[13 empty] | 0 | 0 | 0
VI |  |  |  | Connecting new BPT to the existing BPT | [8 empty] | 0 | 0 | 0
|  | 1 |  | Cost of pipe and specials | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 0 | 0 | 0
|  | 2 |  | On completion | 0.88 | [6 empty] | 0.44 | 0.44 | 0.44 | 50%
[13 empty] | 0 | 0 | 0
VII |  |  |  | RW Pumping Main | [8 empty] | 0 | 0 | 0
|  | 1 |  | On supply of tested pipes | 1.74 | 1.74 | 1.74 | 1.74 | 1.74 | 1.74 | 1.74 | 1.74 | 0 | 0 | 0
|  | 2 |  | On completion of laying inc specials | 0.43 | 0.28 | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 | 0 | 0 | 0
|  | 3 |  | On fixing valves & testing | 0.61 |  | 0.305 | 0.305 | 0.305 | 0.305 | 0.61 | 0.61 | 0 | 0 | 0.305
[13 empty] | 0 | 0 | 0
VIII |  |  |  | Clear Water Pumping Main | [8 empty] | 0 | 0 | 0
|  | 1 |  | On supply of tested pipes | 3.21 | 3.21 | 3.21 | 3.21 | 3.21 | 3.21 | 3.21 | 3.21 | 0 | 0 | 0
|  | 2 |  | On completion of laying inc specials | 0.76 |  | 0.25 | 0.61 | 0.7 | 0.65 | 0.7 | 0.7 | 0 | 0.06 | Nearing completion
|  | 3 |  | On fixing valves & testing | 1.09 |  |  |  | 0.545 | 0.545 | 0.872 | 1.09 | 0.218 | 0 | 0.327
[13 empty] | 0 | 0 | 0
IX |  |  |  | Construction of MS Bridge Support | 1.17 | [5 empty] | 0.585 | 1.17 | 0.585 | 0 | 0.585
[13 empty] | 0 | 0 | 0
X |  |  |  | Pumps | [8 empty] | 0 | 0 | 0
| A | 1 |  | R/W pumps - 2 nos (735 HP) - On supply of tested materials | 6.41 |  | 3.205 | 6.41 | 6.41 | 6.41 | 6.41 | 6.41 | 0 | 0 | 0
|  | 2 |  | On completion of erection | 0.87 | [5 empty] | 0.6525 | 0.87 | 0.2175 | 0 | 80% Nearing completion
| B | 1 |  | C/W pumps - 4 nos (810 HP) - On supply of tested materials | 7.15 |  |  |  | 3.575 | 7.15 | 7.15 | 7.15 | 0 | 0
|  | 2 |  | On completion of erection | 0.15 | [5 empty] | 0.15 | 0.15 | 0 | 0
| C | 1 |  | R/W pumps - 1 nos (750 HP) Existing PM - On supply of tested materials | 3.27 |  |  | 3.27 | 3.27 | 3.27 | 3.27 | 3.27 | 0 | 0 | 0
|  | 2 |  | On completion of erection | 0.05 | [6 empty] | 0.025 | 0.025 | 0.025 | 0
[13 empty] | 0 | 0 | 0
XI |  |  |  | Transformer | [8 empty] | 0 | 0 | 0
| A | 1 |  | 1000 KVA transformer - On supply of transformer | 0.17 |  |  |  |  | 0.17 | 0.17 | 0.17 | 0 | 0 | At site
|  | 2 |  | On supply of related accessories and completion of erection | 0.81 | [5 empty] | 0.2 | 0.405 | 0.205 | 0.405 | 50%
| B | 1 |  | 400 KVA transformer - On supply of transformer | 0.09 |  |  |  |  | 0.09 | 0.09 | 0.09 | 0 | 0 | At site
|  | 2 |  | On supply of related accessories and completion of erection | 0.3 | [5 empty] | 0.075 | 0.15 | 0.075 | 0.15 | 50%
| C | 1 |  | 1000 KVA transformer - On supply of transformer | 0.15 |  |  |  |  | 0.15 | 0.15 | 0.15 | 0 | 0 | At site
|  | 2 |  | On supply of related accessories and completion of erection | 0.87 | [5 empty] | 0.21 | 0.435 | 0.225 | 0.435 | 25%
[13 empty] | 0 | 0 | 0
XII |  |  |  | Internal Electrification & Yard lighting - WTP | 0.13 | [6 empty] | 0.0975 | 0.0975 | 0.0325 | 0
[13 empty] | 0 | 0 | 0
XIII |  |  |  | Other components | [8 empty] | 0 | 0 | 0
|  | 1 | a | SCADA - Supply of materials like PLC, Panel board, Transmittted etc | 4 | [5 empty] | 4 | 4 | 0 | 0 | 4
|  |  | b | Completion of erection | 2 | [6 empty] | 0.8 | 0.8 | 1.2 | 25%
|  | 2 |  | Supply & erection of chlorinator, tonnerhandling / safety equipments | 0.43 | [6 empty] | 0.1075 | 0.1075 | 0.3225 | 0
|  | 3 |  | Solar panel | 0.95 | [5 empty] | 0.76 | 0.76 | 0 | 0.19 | 80% | Connection Pending
|  | 4 |  | Actuators to main valves | 0.48 |  |  | 0.24 | 0.24 | 0.36 | 0.36 | 0.48 | 0.12 | 0 | 75% | Only filter house complete
|  | 5 |  | Formation of road | 0.39 |  |  |  |  | 0.195 | 0.195 | 0.195 | 0 | 0.195 | 0.195
|  | 6 |  | Poviding Lightning arrestor | 0.16 | [6 empty] | 0.16 | 0.16 | 0 | 0
|  | 7 |  | Providing water supply and sanitory arrangements | 0.08 |  |  |  |  | 0.02 | 0.02 | 0.08 | 0.06 | 0 | 0.02
|  | 8 |  | 3-D miniatute model | 0.16 | [6 empty] | 0.16 | 0.16 | 0 | 50%
|  | 9 |  | Providnig screens across dam | 0.1 | [6 empty] | 0.1 | 0.1 | 0 | 0
|  | 10 |  | Land scaping | 0.2 |  |  |  | 0.05 | 0.05 | 0.05 | 0.15 | 0.1 | 0.05 | 0
[13 empty] | 0 | 0 | 0
|  |  |  | Total | 100 | 24.39 | 34.945 | 53.26 | 67.045 | 77.605 | 87.932 | 94.98 | 7.048 | 5.02
[7 empty] | 10.555 | 18.315 | 13.785 | 10.56 | 10.327 | 7.048

## 07-04
|  |  | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01
Sl No | Activity
10MLD PLANT
1 | OHSR - Base slab, beam | RCC - civil works
2 | OHSR - Side wall, top slab | RCC - civil works
3 | OHSR - Side wall, top slab | Plastering
Finishing
4 | Construction of Aerator - Earth work excavation, RCC - civil works | Earth work excavation & PCC
RCC - civil works
5 | Construction of Aerator - Plastering & finishing | Plastering
Finishing
6 | Construction of RW Channel- Plastering & finishing | Plastering
Finishing
7 | Construction of Flash Mixer- Plastering & finishing | Plastering
Finishing
8 | Construction of Chemical store room | Brick/ block work
Plastering
9 | Construction of Office room | Brick/ block work
Plastering
10 | Construction of Substation building | Brick/ block work
Plastering
11 | Construction of c/w pump house | Brick/ block work
Plastering
12 | Construction of Chemical house, Office room -AL door, window | Al. Doors & windows
Finishing
13 | Construction of Alum Lime Tank | Plastering
Finishing
14 | Construction of toilet, sanitary fittings, etc. | Brick/ block work
Sanitary works
15 | Painting & other finishing of c/w ph, office room , etc. | Finishing
Plastering
16 | Construction of Substation, pump house, etc.-Plastering, door, window, Painting & other finishing | Al. Doors & windows
Finishing
17 | Construction of Clarifier | Plastering
Finishing
18 | Construction of filter box - Plastering, Finishing | Plastering
Finishing
300mm Pumping main
19 | C/W P/M from Cheelappara to Peyad | Trenching
Laying of pipes
20 | C/W P/M from Alytti Jn. to Kavinpuram | Trenching
Laying of pipes
21 | C/W P/M from Cheelappara to Peyad | Testing
Valve Chamebr works
22 | C/W P/M from Alytti Jn. to Kavinpuram | Testing
Valve Chamebr works
Mechanical works
23 | Mechanical works-Aerator piping, Flash mixer, agitator, motor unit
24 | Mechanical works-Clarifier, flocculator
25 | Mechanical works-Air blower, flow meter, dial gauges, pies & fittings
26 | Mechanical works-chlorine room, cylinders & accessories
27 | Mechanical works-CI pipes, valves, pvc laterals
28 | Mechanical works - setting up of lab, safety equipments, furnitures
29 | Mechanical works- wash water pumps
Electrical works
30 | Electrical works-electrical fittings & electrification - pump house & all buildings
31 | Electrical works-transformers
32 | Electro-Mechanical works-R/W PUMP HOUSE | Panel, Metering, etc.
89 | Electro-Mechanical works-C/W PUMP HOUSE | Panel, etc.
Miscellaneous works
90 | Compound Wall ,Security cabin and protection works | RCC - civil works
Gates, steps, etc
91 | Formation of road, Land scapping | Formation of road
Land scaping

## Sheet3
|  |  | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01
Sl No | Activity
1 | Design Approvals
2 | Construction of Aerator | Earth work & PCC
RCC- Civil works
Plastering work
Finishing works
3 | Construction of RW Channel & clarified water channel | Earth work & PCC
RCC- Civil works
Plastering work
Finishing works
4 | Construction of Flash Mixer | Earth work & PCC
RCC- Civil works
Plastering work
Finishing works
9 | Construction of Chemical house -Earth work excavation & PCC | Earth work & PCC
RCC- Civil works
10 | Construction of Chemical house -RCC coulmn upto Plinth and Floor concrete
11 | Construction of Chemical house -RCC upto GF
12 | Construction of Chemical house -RCC upto FF
13 | Construction of Chemical house -Brick work/ Solid block work
14 | Construction of Chemical house -Plastering
15 | Construction of Chemical house -AL door, window, Painting & other finishing
16 | Construction of Alum Lime Tank
17 | Construction of Chlorine room- EW Excavation & Foundation upto Plinth
18 | Construction of Chlorine room-RCC work
19 | Construction of Chlorine room-Brick work/Solid block work
20 | Construction of Chlorine room-Plastering, door, window, Painting & other finishing
21 | Construction of Office building with toilet- EW Excavation & Foundation upto Plinth
22 | Construction of Office building with toilet-Brick work/Solid block work
23 | Construction of Office building with toilet-RCC work
24 | Construction of Office building with toilet-Plastering, door, window, Painting & other finishing
25 | Construction of Flocculator -Earth work excavation & PCC
26 | Construction of Flocculator -Mat concreting
27 | Construction of Flocculator -RCC Floor Slab
28 | Construction of Flocculator - RCC Haunch & side wall of Flocculator - 1st lift
29 | Construction of Flocculator - RCC sidewall - 2nd lift
30 | Construction of Flocculator - RCC sidewall - 3rd lift
31 | Construction of Flocculator - Plastering
32 | Construction of Clarifier -Earth work excavation & PCC
33 | Construction of Clarifier -Mat concreting
34 | Construction of Clarifier -RCC Floor Slab
35 | Construction of Clarifier - RCC Haunch & side wall of Clarifier - 1st lift
36 | Construction of Clarifier - RCC sidewall - 2nd lift
37 | Construction of Clarifier - RCC sidewall - 3rd lift
38 | Construction of Clarifier - Plastering
39 | Construction of Clarifier - SS plate for plate settler
40 | Construction of Clarified water channel-Earth work excavation & mat concrete
41 | Construction of Clarified water channel - RCC work for floor slab, sidewall & cover slab
42 | Construction of Clarified water channel - Plastering
43 | Construction of Floating pump house - Bund making
44 | Construction of Floating pump house - Platfrom construction( steel fabrication)
45 | Construction of Floating pump house - platfrom transfer to reservoir
46 | Construction of Floating pump house - HDPE pipe erection & laying
47 | Construction of Floating pump house - Walkway along HDPE pipe length
48 | Construction of Floating pump house - Walkway handrail
49 | Construction of Floating pump house - Pump erection
47 | Construction of wash water tank - Floor slab
48 | Construction of wash water tank - RCC for sidewall
49 | Construction of wash water tank - RCC for roof slab
50 | Construction of wash water tank - Plastering & Finishing
51 | Construction of clear water channel- EW excavation
52 | Construction of clear water channel- CC for Mat foundation & floor slab
53 | Construction of clear water channel- RCC for sidewall and cover slab
54 | Construction of clear water channel- Plastering & Finishing
55 | Construction of substation- EW excavation & PCC
56 | Construction of substation- Plinth beam. RCC column up to 1st level
57 | Construction of substaion- Lintel beam, roof beam, roof slab
58 | Construction of substiton- brick work/block work
59 | Construction of substaion- door, window fixinf, plastering, painting, tiling
60 | Construction of substiton- Electrical works
61 | Mechanical works-Aerator piping, Flash mixer, agitator, motor unit
62 | Mechanical works-Clarifier, flocculator
63 | Mechanical works-Air blower, flow meter, dial gauges, pies & fittings
64 | Mechanical works-chlorine rrom, cylinders & accessories
65 | Mechanical works-CI pipes, valves, pvc laterals
66 | Mechanical works - setting up of lab, safety equipments, furnitures
67 | Mechanical works-pumps
68 | Mechanical works-electrical fittings & electrification
69 | Mechanical works-transformers
70 | Mechanical works-SCADA
71 | Consruction of compound wall
72 | Solar panel, miniature model, miscellaneous works
73 | Formation of road, Land scapping