## SCHEDULE AND CHART
Deposit work (2021-22) Grama panchayat- renovation of Existing well in Raroth ST colony in Meenangadi GP
SL NO | SCHEDULE DETAILS | TARGETTED DATE
1 | ESTIMATE APPROVAL | 2022-07-14
2 | TENDER DATE | 2022-08-06
3 | TENDER OPENING DATE | 2022-08-17
4 | WORK ORDER DATE | 2022-08-26
5 | AGREEMENT DATE | 2022-09-03
6 | SITE HANDED OVER DATE | 2022-09-05
7 | WORK STARTING | 2022-09-07
8 | PROCUREMENT OF PIPE | 2022-09-23
8 | PIPE LAYING | 2022-10-05
9 | PROVIDING FHTCS | 2022-10-22
10 | PROVIDING WATER STORAGE TANK | 2022-10-28
12 | WORK COMPLETION | 2022-11-03