## Sheet1
JJM-Mararikulam (N) Panchayat- Total FHTC- 4982 Nos.
| Activity | Month-1 |  |  |  | Month-2 |  |  |  | Month-3 |  |  |  | Month-4 |  |  |  | Month-5 |  |  |  | Month-6
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
1 | Collection Benificiery List from panchayat | bar: Month-1 1
2 | Field data Collection | bar: Month-1 2 to Month-1 3
3 | Material Testing | bar: Month-1 2 to Month-1 4
4 | Connection Work | bar: Month-2 5 to Month-6 22
5 | Geo-Tagging | bar: Month-2 6 to Month-6 23
6 | FHTC Approval
7 | TPI- Inspection | bar: Month-3 9 to Month-6 23
7 | Preparation of Bill | bar: Month-2 6 to Month-6 24