## Sheet1
SCHEDULE OF WORK PROGRAM
Sl. No. | Description of Work | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17
1 | Site Handover | bar: Week 1
2 | Conveying Materials & Labour | bar: Week 1 to Week 9
3 | Earth Work | bar: Week 2 to Week 13
4 | Laying Pipe | bar: Week 4 to Week 14
5 | Jointing / Interconnection | bar: Week 12 to Week 15
6 | Testing Pipes | bar: Week 14 to Week 16
7 | Backfilling / Compaction | bar: Week 10 to Week 16
8 | Road Restoration Work | bar: Week 12 to Week 17
9 | Documentation / Billing | bar: Week 17