## Sheet1
JJmPhase 1-(Balance Fund)-Moopainad Panchayath-Providing Functional House hold tap connections in moopinad GP
Start Date | End Date | Percetage
10.03.2022 | 31.03.2022 | 10
01.04.2022 | 30.04.2022 | 20
01.05.2022 | 31.05.2022 | 40
01.06.2022 | 30.06.2022 | 60
01.07.2022 | 31.07.2022 | 75
01.08.2022 | 31.08.2022 | 90
01.09.2022 | 30.09.2022 | 100

## Sheet2
Deposit work -(2021-2022)-(PMGSY) - ARWSS to Krishnagiri Purakkadi and Ambalavayal Villages Relaying of damaged distribution lines along Manjappara Nellarachal road.
SL NO | ACTIVITY | DATE | PERCENTAGE
1 | Supply of Pipes | 2022-04-22 | 5%
2 | Excavating Trenches | 2022-04-22 | 15%
3 | Laying HDPE Pipes | 2022-05-22 | 40%
4 | Providing FHTCs | 2022-06-22 | 60%
5 | Testing and Comitioning | 2022-07-22 | 100%