## Sheet1
JJM - Phase I - ALIPPARAMBA - THAZHEKKODE Gramma Panchayath - PACKAGE III
Description | WORK PLAN
| 2022-05-01 | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | 2023-01-01 | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER
Suppl of pipes and specials
Laying and testing of pipes | bar: FEBRUARY to JULY
providing FHTCs
Trial run and commissiong