## PUTHIYAPADI COLONY
Deposit work (2021-22) Ambalavayal Grama Panchayat- Pipe line extension to Puthiyapadi colony
SL NO | SCHEDULE DETAILS | TARGETTED DATE
1 | ESTIMATE APPROVAL | 2022-07-14
2 | TENDER DATE | 2022-08-06
3 | TENDER OPENING DATE | 2022-08-17
4 | WORK ORDER DATE | 2022-08-26
5 | AGREEMENT DATE | 2022-09-03
6 | SITE HANDED OVER DATE | 2022-09-05
7 | WORK STARTING | 2022-09-10
8 | PROCUREMENT OF PIPE | 2022-09-20
9 | PIPE LAYING | 2022-10-05
10 | WORK COMPLETION | 2022-11-21

## NELLISSERY SHAJI
Deposit work (2021-22) Ambalavayal Grama Panchayat- Pipe line extension to Nellissery Shaji house area
SL NO | SCHEDULE DETAILS | TARGETTED DATE
1 | ESTIMATE APPROVAL | 2022-07-14
2 | TENDER DATE | 2022-08-06
3 | TENDER OPENING DATE | 2022-08-17
4 | WORK ORDER DATE | 2022-08-26
5 | AGREEMENT DATE | 2022-09-03
6 | SITE HANDED OVER DATE | 2022-09-05
7 | WORK STARTING | 2022-09-07
8 | PROCUREMENT OF PIPE | 2022-09-25
9 | PIPE LAYING | 2022-10-10
10 | WORK COMPLETION | 2022-11-16

## SECRETARY KAVALA
Deposit work (2021-22) Ambalavayal Grama Panchayat- Pipe line extension to Secretary Kavala
SL NO | SCHEDULE DETAILS | TARGETTED DATE
1 | ESTIMATE APPROVAL | 2022-07-14
2 | TENDER DATE | 2022-08-06
3 | TENDER OPENING DATE | 2022-08-17
4 | WORK ORDER DATE | 2022-08-26
5 | AGREEMENT DATE | 2022-09-03
6 | SITE HANDED OVER DATE | 2022-09-03
7 | WORK STARTING | 2022-09-10
8 | PROCUREMENT OF PIPE | 2022-09-25
9 | PIPE LAYING | 2022-10-10
10 | WORK COMPLETION | 2022-11-10

## KARIMAMKUNNU AMBALAMKAVU
Deposit work (2021-22) Ambalavayal Grama Panchayat- Pipe line extension to Karimamkunnu Ambalamkavu
SL NO | SCHEDULE DETAILS | TARGETTED DATE
1 | ESTIMATE APPROVAL | 2022-07-14
2 | TENDER DATE | 2022-08-06
3 | TENDER OPENING DATE | 2022-08-17
4 | WORK ORDER DATE | 2022-08-26
5 | AGREEMENT DATE | 2022-09-03
6 | SITE HANDED OVER DATE | 2022-09-05
7 | WORK STARTING | 2022-09-12
8 | PROCUREMENT OF PIPE | 2022-09-25
9 | PIPE LAYING | 2022-10-10
10 | WORK COMPLETION | 2022-11-15