## Sheet3
WORK SCHEDULE CHART
JJM- WSS to Alakkode and adjoining Panchayaths in Kannur District-Surveying distribution networks in Payyavoor,Eruvessi,Naduvil, Alakkode, Udayagiri, Peringome-Vayakkara and Cherupuzha Panchayaths
Date |  | Details of work
Overall Work Schedule
2021-05-01 | 0% | Survey work starting in Payyavoor Panchayath
2021-05-08 | 10% | Survey work in progress in Payyavoor Panchayath and Eruveshi Panchayath
2021-05-15 | 20% | Survey work in completion in Payyavoor Panchayath and Eruveshi Panchayath
2021-05-22 | 30% | Survey work in progress in Alakode, Naduvil, and Udayagiri Panchayaths
2021-05-29 | 40% | Survey work in progress in Alakode, Naduvil, and Udayagiri Panchayaths
2021-06-05 | 50% | Survey work in progress in Alakode, Naduvil, and Udayagiri Panchayaths
2021-06-12 | 60% | Survey work completion in Alakode, Naduvil, and Udayagiri Panchayaths
2021-06-19 | 70% | Survey work in progress in Cherupuzha and Peringome Vayakkara Panchayaths
2021-06-26 | 80% | Survey work in progress in Cherupuzha and Peringome Vayakkara Panchayaths
2021-07-03 | 90% | Survey work completion in Cherupuzha and Peringome Vayakkara Panchayaths
2021-07-10 | 100% | Final submission of design drawings