## Package I
Name of Work:
Name of work : KIIFB - Augumentation of Water Supply Schemes To Angamaly Constituency . Part I - package I - Construction of well cum pump house, laying raw water pumping main
Administrative Sanction :12-11-2018 (KIIFB saction date)
Technical Sanction: Nil
SL.No | Activity | Start | Finish | 2021-12-19 | 2022-01-19 | 2022-02-19 | 2022-03-19 | 2022-04-19 | 2022-05-19 | 2022-06-19 | 2022-07-19 | 2022-08-19 | 2022-09-19 | 2022-10-19 | 2022-11-19 | 2022-12-19 | 2023-01-19 | 2023-02-19 | 2023-03-19 | 2023-04-19 | 2023-05-19 | 2023-06-19 | 2023-07-19 | 2023-08-19 | 2023-09-19 | 2023-10-19
1 | Preparation of working estimate | 2021-12-11 | 2022-07-30
2 | Technical sanction | 2022-08-01 | 2022-08-10
3 | NIIT preparation | 2022-05-08 | 15.8-2022
4 | Tendering | 16.8-2022 | 30.8-2022
5 | Tender Approval | 1.9-2022 | 7.9-2022
6 | Agreement execution | 8.9-2022 | 23.9-2022 | [9 empty] | `
7 | Construction of well cum pump house | 24.9-2022 | 2023-06-16
8 | Procurment of pipes and specials | 24.9.2022 | 10.11-2022
9 | Laying Raw water pumping main | 15.10-2022 | 2023-08-25
10 | Procurment of Transformer | 24.9.2022 | 2022-10-22
11 | Procurment of Raw water pump sets | 2022-11-22 | 2023-02-23
12 | Erection of RW pump sets | 2023-03-28 | 2022-04-27
13 | Erection of Transformer and allied work in RWPH | 2022-07-23 | 31-09-2023
14 | Approval from electrical Inspectrate | 2023-09-05 | 31-09-2023
15 | Power connection from KSEB | 2023-10-01 | 2023-10-15
16 | Trial run | 2023-10-15 | 2023-10-25
17 | commissioning | 2023-10-30 | 2023-10-30

## Package II
Name of work : KIIFB - Augumentation of Water Supply Schemes To Angamaly Constituency - Part I - package II - Construction of 17 mld water treatment plant , laying raw water pumping main
Administrative Sanction :12-11-2018 (KIIFB saction date)
Technical Sanction: Nil
SL.No | Activity | Start | Finish | 2021-12-19 | 2022-01-19 | 2022-02-19 | 2022-03-19 | 2022-04-19 | 2022-05-19 | 2022-06-19 | 2022-07-19 | 2022-08-19 | 2022-09-19 | 2022-10-19 | 2022-11-19 | 2022-12-19 | 2023-01-19 | 2023-02-19 | 2023-03-19 | 2023-04-19 | 2023-05-19 | 2023-06-19 | 2023-07-19 | 2023-08-19 | 2023-09-19 | 2023-10-19
1 | Preparation of working estimate | 2021-12-11 | 20.8.2022
2 | Technical sanction | 21.8.2022 | 28.8.2022
3 | NIIT preparation | 29.8.2022 | 7.9.2022
4 | Tendering | 8.9.2022 | 18.9.2022
5 | Tender Approval | 19.9.2022 | 1.10.2022
6 | Agreement execution | 2.10-2022 | 17.10.2022
7 | Construction of water treatment plant | 18.10-2022 | 15.10-2023
| Construction of OHSR | 25.10.2022 | 2023-06-01
8 | Procurment of pipes and specials | 18.10.202022 | 18.1.2023
9 | Laying Raw water pumping main | 15.11.2023 | 2023-08-25
10 | Procurment of Transformer | 15.11.2022 | 30.12.2022
11 | Procurment of clear water pump sets | 2022-12-22 | 2023-03-23
12 | Erection of CW pump sets | 2023-04-28 | 2023-06-27
13 | Erection of Transformer and allied work in RWPH | 2022-07-23 | 2023-09-30
14 | Approval from electrical Inspectrate | 2023-09-05 | 31-09-2023
15 | Power connection from KSEB | 2023-10-01 | 2023-10-14
16 | Trial run | 2023-10-14 | 2023-10-29
17 | commissioning | 2023-10-30 | 2023-10-30

## Package III
Name of work : KIIFB - Augumentation of Water Supply Schemes To Angamaly Constituency - Part I - package III - laying clear water pumping main, Construction of OHSRs
Administrative Sanction :12-11-2018 (KIIFB saction date)
Technical Sanction: Nil
SL.No | Activity | Start | Finish | 2021-12-19 | 2022-01-19 | 2022-02-19 | 2022-03-19 | 2022-04-19 | 2022-05-19 | 2022-06-19 | 2022-07-19 | 2022-08-19 | 2022-09-19 | 2022-10-19 | 2022-11-19 | 2022-12-19 | 2023-01-19 | 2023-02-19 | 2023-03-19 | 2023-04-19 | 2023-05-19 | 2023-06-19 | 2023-07-19 | 2023-08-19 | 2023-09-19 | 2023-10-19
1 | Preparation of working estimate | 2021-12-11 | 30.8.2022
2 | Technical sanction | 1.9.2022 | 5.9.2022
3 | NIIT preparation | 6.9.2022 | 13.9.2022
4 | Tendering | 14.9.2022 | 25.9.2022
5 | Tender Approval | 26.9.2022 | 30.9.2022
6 | Agreement execution | 1.10.2022 | 15.10.2022
| Construction of OHSRs | 16.10.2022 | 2023-06-20
8 | Procurment of pipes and specials | 16.10.2022 | 30.11.2022
9 | Laying clear water pumping main | 15.11.2022 | 2023-08-25
10 | Procurment of Transformer | 25.11.2022 | 15.1.2023
11 | Procurment of clear water pump sets | 2022-12-22 | 2023-04-23
12 | Erection of CW pump sets | 2023-05-28 | 2023-07-27
13 | Erection of Transformer and allied work in RWPH | 2023-06-23 | 2023-08-31
14 | Approval from electrical Inspectrate | 2023-08-05 | 2023-08-31
15 | Power connection from KSEB | 2023-09-01 | 2023-10-14
16 | Trial run | 2023-10-14 | 2023-10-29
17 | commissioning | 2023-10-30 | 2023-10-30