## Sheet1
Sl.No | Activity | Dates | Percentage
1 | Supply of Pipes | 2022-02-01 | 2%
2 | Excavating Trenches | 2022-04-01 | 10%
3 | Laying of Pipes/Providing FHTCs | 2022-05-01 | 15%
4 | Providing FHTCs | 2022-06-01 | 20%
5 | Construction of Tank | 2022-07-01 | 25%
5 | Construction ofValve Chember | 2022-10-01 | 27%
6 | Supply errection of pump sets | 2022-12-01 | 30%
7 | Laying Distribution line | 2023-03-01 | 50%
8 | Providing FHTCs | 2023-05-01 | 55%
9 | Renovation Works at WTP | 2023-06-01 | 60%
10 | Providing FHTCs/laying Distribution line | 2023-09-01 | 72%
11 | Construction of Compound wall | 2023-12-01 | 80%
12 | Construction of Settling tank/valve chembers /FHTCs | 2024-01-01 | 85%
13 | Road Restoration work | 2024-02-01 | 90%
14 | Testing and Commissioning | 2024-03-01 | 100%