## Sheet1
COMPONENTS | START DATE | DAYS TO COMPLETE
Agreement executed | 2021-05-24 | 24
24
5
supply of materials | 2021-05-19 | 10
13
10
FHTCs work started for inauguration | 2021-06-21 | 1
10
30
Survey work | 2021-06-22 | 18
93
45
FHTCs work | 2021-06-23 | 250
30
21
laying work | 2021-06-21 | 250
65
49
line testing and third party inspection | 2021-09-01 | 200
30
30
Commissioning and Other Miscellaneous Activities | 2022-05-15 | 15