## Schedule Chart
Components | Start Date | End date | Duration
Construction of Intake well cum pump house at Thumbathadam | 2022-11-15 | 2023-08-15 | 273
Construction of 4.50m High RCC weir at Thumbathadam | 2022-11-15 | 2023-11-15 | 365 | 44774 | 2023-12-01
Construction of 1.75LL Booster sump and pump house at Kuttur | 2022-11-01 | 2023-05-01 | 181
Construction of 4MLD WTP at Kannadipoyyil | 2022-08-01 | 2023-05-01 | 273
Construction of 6.5LL OHSR at Kannadipoyyil | 2022-09-01 | 2023-06-01 | 273
Construction of 2.00LL Clear water sump and clear water pump house at Kannadipoyyil | 2022-08-01 | 2023-04-01 | 243
Construction of 4.50LL OHSTR at Vellora | 2022-10-01 | 2023-07-01 | 273
Construction of 0.50LL BP tank at Palayad | 2022-09-01 | 2023-03-01 | 181
Supplying and laying 300 mm DI K9 Raw water pumping main | 2022-10-01 | 2023-04-01 | 182
Supplying and laying 200 mm DI K9 Clear water pumping main | 2022-10-01 | 2023-05-01 | 212
Supplying and laying 110 mm PVC Clear water transmission main | 2022-10-01 | 2023-01-01 | 92
Supplying ,erecting, commissioning of raw water and clear water pumpsets | 2023-07-01 | 2023-08-01 | 31
Supplying and laying distribution pipe lines | 2022-08-01 | 2023-11-01 | 457
Proving FHTCs | 2022-08-01 | 2023-11-01 | 457
Trial Running and Commissioning | 2023-08-01 | 2023-12-01 | 122
Formulas:
Start Date = [Start Date, row above]