## Sheet1
[5 empty] | 2021-12-30 | [6 empty] | 2022-01-06 | [6 empty] | 2022-01-13 | [6 empty] | 2022-01-20 | [6 empty] | 2022-01-27 | [6 empty] | 2022-02-03 | [6 empty] | 2022-02-10 | [6 empty] | 2022-02-17 | [6 empty] | 2022-02-24 | [6 empty] | 2022-03-03 | [6 empty] | 2022-03-10 | [6 empty] | 2022-03-17 | [6 empty] | 2022-03-24 | [6 empty] | 2022-03-31 | [6 empty] | 2022-04-07 | [6 empty] | 2022-04-14 | [6 empty] | 2022-04-21 | [6 empty] | 2022-04-28 | [6 empty] | 2022-05-05 | [6 empty] | 2022-05-12 | [6 empty] | 2022-05-19 | [6 empty] | 2022-05-26 | [6 empty] | 2022-06-02 | [6 empty] | 2022-06-09 | [6 empty] | 2022-06-16 | [6 empty] | 2022-06-23 | [6 empty] | 2022-06-30 | [6 empty] | 2022-07-07 | [6 empty] | 2022-07-14 | [6 empty] | 2022-07-21 | [6 empty] | 2022-07-28 | [6 empty] | 2022-08-04 | [6 empty] | 2022-08-11 | [6 empty] | 2022-08-18 | [6 empty] | 2022-08-25 | [6 empty] | 2022-09-01 | [6 empty] | 2022-09-08 | [6 empty] | 2022-09-15 | [6 empty] | 2022-09-22 | [6 empty] | 2022-09-29 | [6 empty] | 2022-10-06 | [6 empty] | 2022-10-13 | [6 empty] | 2022-10-20 | [6 empty] | 2022-10-27 | [6 empty] | 2022-11-03 | [6 empty] | 2022-11-10 | [6 empty] | 2022-11-17 | [6 empty] | 2022-11-24 | [6 empty] | 2022-12-01 | [6 empty] | 2022-12-08 | [6 empty] | 2022-12-15 | [6 empty] | 2022-12-22 | [6 empty] | 2022-12-29 | [6 empty] | 2023-01-05 | [6 empty] | 2023-01-12 | [6 empty] | 2023-01-19 | [6 empty] | 2023-01-26 | [6 empty] | 2023-02-02 | [6 empty] | 2023-02-09 | [6 empty] | 2023-02-16 | [6 empty] | 2023-02-23 | [6 empty] | 2023-03-02 | [6 empty] | 2023-03-09 | [6 empty] | 2023-03-16 | [6 empty] | 2023-03-23 | [6 empty] | 2023-03-30 | [6 empty] | 2023-04-06 | [6 empty] | 2023-04-13 | [6 empty] | 2023-04-20 | [6 empty] | 2023-04-27 | [6 empty] | 2023-05-04 | [6 empty] | 2023-05-11 | [6 empty] | 2023-05-18 | [6 empty] | 2023-05-25 | [6 empty] | 2023-06-01 | [6 empty] | 2023-06-08 | [6 empty] | 2023-06-15 | [6 empty] | 2023-06-22 | [6 empty] | 2023-06-29 | [6 empty] | 2023-07-06 | [6 empty] | 2023-07-13 | [6 empty] | 2023-07-20 | [6 empty] | 2023-07-27 | [6 empty] | 2023-08-03 | [6 empty] | 2023-08-10
[5 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To | [6 empty] | To
[5 empty] | 2022-01-05 | [6 empty] | 2022-01-12 | [6 empty] | 2022-01-19 | [6 empty] | 2022-01-26 | [6 empty] | 2022-02-02 | [6 empty] | 2022-02-09 | [6 empty] | 2022-02-16 | [6 empty] | 2022-02-23 | [6 empty] | 2022-03-02 | [6 empty] | 2022-03-09 | [6 empty] | 2022-03-16 | [6 empty] | 2022-03-23 | [6 empty] | 2022-03-30 | [6 empty] | 2022-04-06 | [6 empty] | 2022-04-13 | [6 empty] | 2022-04-20 | [6 empty] | 2022-04-27 | [6 empty] | 2022-05-04 | [6 empty] | 2022-05-11 | [6 empty] | 2022-05-18 | [6 empty] | 2022-05-25 | [6 empty] | 2022-06-01 | [6 empty] | 2022-06-08 | [6 empty] | 2022-06-15 | [6 empty] | 2022-06-22 | [6 empty] | 2022-06-29 | [6 empty] | 2022-07-06 | [6 empty] | 2022-07-13 | [6 empty] | 2022-07-20 | [6 empty] | 2022-07-27 | [6 empty] | 2022-08-03 | [6 empty] | 2022-08-10 | [6 empty] | 2022-08-17 | [6 empty] | 2022-08-24 | [6 empty] | 2022-08-31 | [6 empty] | 2022-09-07 | [6 empty] | 2022-09-14 | [6 empty] | 2022-09-21 | [6 empty] | 2022-09-28 | [6 empty] | 2022-10-05 | [6 empty] | 2022-10-12 | [6 empty] | 2022-10-19 | [6 empty] | 2022-10-26 | [6 empty] | 2022-11-02 | [6 empty] | 2022-11-09 | [6 empty] | 2022-11-16 | [6 empty] | 2022-11-23 | [6 empty] | 2022-11-30 | [6 empty] | 2022-12-07 | [6 empty] | 2022-12-14 | [6 empty] | 2022-12-21 | [6 empty] | 2022-12-28 | [6 empty] | 2023-01-04 | [6 empty] | 2023-01-11 | [6 empty] | 2023-01-18 | [6 empty] | 2023-01-25 | [6 empty] | 2023-02-01 | [6 empty] | 2023-02-08 | [6 empty] | 2023-02-15 | [6 empty] | 2023-02-22 | [6 empty] | 2023-03-01 | [6 empty] | 2023-03-08 | [6 empty] | 2023-03-15 | [6 empty] | 2023-03-22 | [6 empty] | 2023-03-29 | [6 empty] | 2023-04-05 | [6 empty] | 2023-04-12 | [6 empty] | 2023-04-19 | [6 empty] | 2023-04-26 | [6 empty] | 2023-05-03 | [6 empty] | 2023-05-10 | [6 empty] | 2023-05-17 | [6 empty] | 2023-05-24 | [6 empty] | 2023-05-31 | [6 empty] | 2023-06-07 | [6 empty] | 2023-06-14 | [6 empty] | 2023-06-21 | [6 empty] | 2023-06-28 | [6 empty] | 2023-07-05 | [6 empty] | 2023-07-12 | [6 empty] | 2023-07-19 | [6 empty] | 2023-07-26 | [6 empty] | 2023-08-02 | [6 empty] | 2023-08-09 | [6 empty] | 2023-08-16 | [6 empty] | 0
ID | Task Name | Start | End | Days | 2021-12-30 | 2021-12-31 | 2022-01-01 | 2022-01-02 | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-07 | 2022-01-08 | 2022-01-09 | 2022-01-10 | 2022-01-11 | 2022-01-12 | 2022-01-13 | 2022-01-14 | 2022-01-15 | 2022-01-16 | 2022-01-17 | 2022-01-18 | 2022-01-19 | 2022-01-20 | 2022-01-21 | 2022-01-22 | 2022-01-23 | 2022-01-24 | 2022-01-25 | 2022-01-26 | 2022-01-27 | 2022-01-28 | 2022-01-29 | 2022-01-30 | 2022-01-31 | 2022-02-01 | 2022-02-02 | 2022-02-03 | 2022-02-04 | 2022-02-05 | 2022-02-06 | 2022-02-07 | 2022-02-08 | 2022-02-09 | 2022-02-10 | 2022-02-11 | 2022-02-12 | 2022-02-13 | 2022-02-14 | 2022-02-15 | 2022-02-16 | 2022-02-17 | 2022-02-18 | 2022-02-19 | 2022-02-20 | 2022-02-21 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-02-26 | 2022-02-27 | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-12 | 2022-03-13 | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-18 | 2022-03-19 | 2022-03-20 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-26 | 2022-03-27 | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-02 | 2022-04-03 | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-09 | 2022-04-10 | 2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-14 | 2022-04-15 | 2022-04-16 | 2022-04-17 | 2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-22 | 2022-04-23 | 2022-04-24 | 2022-04-25 | 2022-04-26 | 2022-04-27 | 2022-04-28 | 2022-04-29 | 2022-04-30 | 2022-05-01 | 2022-05-02 | 2022-05-03 | 2022-05-04 | 2022-05-05 | 2022-05-06 | 2022-05-07 | 2022-05-08 | 2022-05-09 | 2022-05-10 | 2022-05-11 | 2022-05-12 | 2022-05-13 | 2022-05-14 | 2022-05-15 | 2022-05-16 | 2022-05-17 | 2022-05-18 | 2022-05-19 | 2022-05-20 | 2022-05-21 | 2022-05-22 | 2022-05-23 | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-27 | 2022-05-28 | 2022-05-29 | 2022-05-30 | 2022-05-31 | 2022-06-01 | 2022-06-02 | 2022-06-03 | 2022-06-04 | 2022-06-05 | 2022-06-06 | 2022-06-07 | 2022-06-08 | 2022-06-09 | 2022-06-10 | 2022-06-11 | 2022-06-12 | 2022-06-13 | 2022-06-14 | 2022-06-15 | 2022-06-16 | 2022-06-17 | 2022-06-18 | 2022-06-19 | 2022-06-20 | 2022-06-21 | 2022-06-22 | 2022-06-23 | 2022-06-24 | 2022-06-25 | 2022-06-26 | 2022-06-27 | 2022-06-28 | 2022-06-29 | 2022-06-30 | 2022-07-01 | 2022-07-02 | 2022-07-03 | 2022-07-04 | 2022-07-05 | 2022-07-06 | 2022-07-07 | 2022-07-08 | 2022-07-09 | 2022-07-10 | 2022-07-11 | 2022-07-12 | 2022-07-13 | 2022-07-14 | 2022-07-15 | 2022-07-16 | 2022-07-17 | 2022-07-18 | 2022-07-19 | 2022-07-20 | 2022-07-21 | 2022-07-22 | 2022-07-23 | 2022-07-24 | 2022-07-25 | 2022-07-26 | 2022-07-27 | 2022-07-28 | 2022-07-29 | 2022-07-30 | 2022-07-31 | 2022-08-01 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 | 2022-08-06 | 2022-08-07 | 2022-08-08 | 2022-08-09 | 2022-08-10 | 2022-08-11 | 2022-08-12 | 2022-08-13 | 2022-08-14 | 2022-08-15 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19 | 2022-08-20 | 2022-08-21 | 2022-08-22 | 2022-08-23 | 2022-08-24 | 2022-08-25 | 2022-08-26 | 2022-08-27 | 2022-08-28 | 2022-08-29 | 2022-08-30 | 2022-08-31 | 2022-09-01 | 2022-09-02 | 2022-09-03 | 2022-09-04 | 2022-09-05 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09 | 2022-09-10 | 2022-09-11 | 2022-09-12 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-17 | 2022-09-18 | 2022-09-19 | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-23 | 2022-09-24 | 2022-09-25 | 2022-09-26 | 2022-09-27 | 2022-09-28 | 2022-09-29 | 2022-09-30 | 2022-10-01 | 2022-10-02 | 2022-10-03 | 2022-10-04 | 2022-10-05 | 2022-10-06 | 2022-10-07 | 2022-10-08 | 2022-10-09 | 2022-10-10 | 2022-10-11 | 2022-10-12 | 2022-10-13 | 2022-10-14 | 2022-10-15 | 2022-10-16 | 2022-10-17 | 2022-10-18 | 2022-10-19 | 2022-10-20 | 2022-10-21 | 2022-10-22 | 2022-10-23 | 2022-10-24 | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-28 | 2022-10-29 | 2022-10-30 | 2022-10-31 | 2022-11-01 | 2022-11-02 | 2022-11-03 | 2022-11-04 | 2022-11-05 | 2022-11-06 | 2022-11-07 | 2022-11-08 | 2022-11-09 | 2022-11-10 | 2022-11-11 | 2022-11-12 | 2022-11-13 | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-17 | 2022-11-18 | 2022-11-19 | 2022-11-20 | 2022-11-21 | 2022-11-22 | 2022-11-23 | 2022-11-24 | 2022-11-25 | 2022-11-26 | 2022-11-27 | 2022-11-28 | 2022-11-29 | 2022-11-30 | 2022-12-01 | 2022-12-02 | 2022-12-03 | 2022-12-04 | 2022-12-05 | 2022-12-06 | 2022-12-07 | 2022-12-08 | 2022-12-09 | 2022-12-10 | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-14 | 2022-12-15 | 2022-12-16 | 2022-12-17 | 2022-12-18 | 2022-12-19 | 2022-12-20 | 2022-12-21 | 2022-12-22 | 2022-12-23 | 2022-12-24 | 2022-12-25 | 2022-12-26 | 2022-12-27 | 2022-12-28 | 2022-12-29 | 2022-12-30 | 2022-12-31 | 2023-01-01 | 2023-01-02 | 2023-01-03 | 2023-01-04 | 2023-01-05 | 2023-01-06 | 2023-01-07 | 2023-01-08 | 2023-01-09 | 2023-01-10 | 2023-01-11 | 2023-01-12 | 2023-01-13 | 2023-01-14 | 2023-01-15 | 2023-01-16 | 2023-01-17 | 2023-01-18 | 2023-01-19 | 2023-01-20 | 2023-01-21 | 2023-01-22 | 2023-01-23 | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-27 | 2023-01-28 | 2023-01-29 | 2023-01-30 | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-03 | 2023-02-04 | 2023-02-05 | 2023-02-06 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-10 | 2023-02-11 | 2023-02-12 | 2023-02-13 | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-17 | 2023-02-18 | 2023-02-19 | 2023-02-20 | 2023-02-21 | 2023-02-22 | 2023-02-23 | 2023-02-24 | 2023-02-25 | 2023-02-26 | 2023-02-27 | 2023-02-28 | 2023-03-01 | 2023-03-02 | 2023-03-03 | 2023-03-04 | 2023-03-05 | 2023-03-06 | 2023-03-07 | 2023-03-08 | 2023-03-09 | 2023-03-10 | 2023-03-11 | 2023-03-12 | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-16 | 2023-03-17 | 2023-03-18 | 2023-03-19 | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24 | 2023-03-25 | 2023-03-26 | 2023-03-27 | 2023-03-28 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 2023-04-01 | 2023-04-02 | 2023-04-03 | 2023-04-04 | 2023-04-05 | 2023-04-06 | 2023-04-07 | 2023-04-08 | 2023-04-09 | 2023-04-10 | 2023-04-11 | 2023-04-12 | 2023-04-13 | 2023-04-14 | 2023-04-15 | 2023-04-16 | 2023-04-17 | 2023-04-18 | 2023-04-19 | 2023-04-20 | 2023-04-21 | 2023-04-22 | 2023-04-23 | 2023-04-24 | 2023-04-25 | 2023-04-26 | 2023-04-27 | 2023-04-28 | 2023-04-29 | 2023-04-30 | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-05 | 2023-05-06 | 2023-05-07 | 2023-05-08 | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-12 | 2023-05-13 | 2023-05-14 | 2023-05-15 | 2023-05-16 | 2023-05-17 | 2023-05-18 | 2023-05-19 | 2023-05-20 | 2023-05-21 | 2023-05-22 | 2023-05-23 | 2023-05-24 | 2023-05-25 | 2023-05-26 | 2023-05-27 | 2023-05-28 | 2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-06-01 | 2023-06-02 | 2023-06-03 | 2023-06-04 | 2023-06-05 | 2023-06-06 | 2023-06-07 | 2023-06-08 | 2023-06-09 | 2023-06-10 | 2023-06-11 | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-15 | 2023-06-16 | 2023-06-17 | 2023-06-18 | 2023-06-19 | 2023-06-20 | 2023-06-21 | 2023-06-22 | 2023-06-23 | 2023-06-24 | 2023-06-25 | 2023-06-26 | 2023-06-27 | 2023-06-28 | 2023-06-29 | 2023-06-30 | 2023-07-01 | 2023-07-02 | 2023-07-03 | 2023-07-04 | 2023-07-05 | 2023-07-06 | 2023-07-07 | 2023-07-08 | 2023-07-09 | 2023-07-10 | 2023-07-11 | 2023-07-12 | 2023-07-13 | 2023-07-14 | 2023-07-15 | 2023-07-16 | 2023-07-17 | 2023-07-18 | 2023-07-19 | 2023-07-20 | 2023-07-21 | 2023-07-22 | 2023-07-23 | 2023-07-24 | 2023-07-25 | 2023-07-26 | 2023-07-27 | 2023-07-28 | 2023-07-29 | 2023-07-30 | 2023-07-31 | 2023-08-01 | 2023-08-02 | 2023-08-03 | 2023-08-04 | 2023-08-05 | 2023-08-06 | 2023-08-07 | 2023-08-08 | 2023-08-09 | 2023-08-10 | 2023-08-11 | 2023-08-12 | 2023-08-13 | 2023-08-14 | 2023-08-15 | 2023-08-16 | 2023-08-17 | 2023-08-18 | 2023-08-19 | 2023-08-20 | 2023-08-21 | 2023-08-22
1 | JAL JEEVAN MISSION WATER SUPPLY SCHEME TO KOTTAYI GRAMA PANCHAYATH IN ALATHUR TALUK OF PALAKKAD DISTRICT | 2021-12-30 | 2023-06-22 | 539
2 | Project Start | 2021-12-30 | 2023-06-22 | 539
3 | Pre-Construction Work | 2021-12-30 | 2022-02-15 | 47
4 | TS, Tender Process & Excecution of work contract | 2021-12-30 | 2022-01-26 | 27
5 | Technical Bid Opening | 2021-12-30 | 2021-12-31 | 1
6 | Price bid Opening | 2022-01-11 | 2022-01-12 | 1
7 | Tender approval | 2022-01-12 | 2022-01-21 | 7
8 | Award of Work | 2022-01-21 | 2022-01-24 | 1
9 | Signing of Agreement with Contractor | 2022-01-24 | 2022-01-25 | 1
10 | Site Hand over to the contractor | 2022-01-26 | 2022-01-26 | 0
11 | PWD road approval | 2022-01-25 | 2022-02-15 | 15
12 | Contract work | 2022-01-13 | 2023-05-05 | 477
13 | Construction of WELL CUM Pump house | 2022-01-27 | 2023-03-30 | 427
14 | Earthern bund | 2022-01-27 | 2022-02-14 | 12
15 | Rock blasting | 2022-02-15 | 2022-05-10 | 60
16 | Ceiling cover slab | 2022-05-11 | 2022-05-27 | 12
17 | Steining Ist Lift | 2022-05-30 | 2022-06-29 | 22
18 | Steining 2nd Lift | 2022-06-30 | 2022-07-28 | 20
19 | Steining 3rd Lift | 2022-07-29 | 2022-08-24 | 18
20 | Steining 4th Lift | 2022-08-25 | 2022-09-16 | 16
21 | Steining 5th Lift | 2022-09-19 | 2022-10-07 | 14
22 | Steining 6th Lift | 2022-10-10 | 2022-10-26 | 12
23 | Steining 7th Lift | 2022-10-27 | 2022-11-10 | 10
24 | Steining 8th Lift | 2022-11-11 | 2022-11-23 | 8
25 | Steining 9th Lift | 2022-11-24 | 2022-12-06 | 8
26 | Steining 10th Lift | 2022-12-07 | 2022-12-19 | 8
27 | Steining 11th Lift | 2022-12-20 | 2022-12-30 | 8
28 | Steining 12th Lift | 2023-01-02 | 2023-01-12 | 8
29 | Floor beam and slab | 2023-01-13 | 2023-01-27 | 10
30 | Side wall | 2023-01-30 | 2023-02-13 | 10
31 | Roof beam | 2023-02-14 | 2023-02-24 | 8
32 | Roof slab | 2023-02-27 | 2023-03-13 | 10
33 | Testing and Commissioning | 2023-03-14 | 2023-03-28 | 10
34 | Finishing works | 2022-11-24 | 2023-03-30 | 90
35 | Construction of 10 LL OHSR | 2022-01-13 | 2022-12-15 | 336
36 | Earth work for Foundation | 2022-01-13 | 2022-01-24 | 7
37 | Structural work upto plinth beam | 2022-01-25 | 2022-02-08 | 10
38 | Structural work upto Ist Brace | 2022-02-09 | 2022-02-23 | 10
39 | Structural Work upto IInd Brace | 2022-02-24 | 2022-03-10 | 10
40 | Structural Work upto III rd Brace | 2022-03-11 | 2022-03-29 | 12
41 | Structural Work upto IV th Brace | 2022-03-30 | 2022-04-15 | 12
42 | Structural work upto floor slab | 2022-03-30 | 2022-04-20 | 15
43 | Structural work upto Roof slab | 2022-04-21 | 2022-06-02 | 30
44 | Supply and erection of columns pipes valves etc | 2022-05-11 | 2022-06-08 | 20
45 | Supply and erection of Flow meters | 2022-06-09 | 2022-06-16 | 5
46 | Testing and Commissioning | 2022-12-08 | 2022-12-15 | 5
47 | Finishing works | 2022-04-21 | 2022-06-23 | 45
48 | Construction of 5 LL OHSR | 2022-01-13 | 2022-06-06 | 144
49 | Earth work for Foundation | 2022-01-13 | 2022-01-24 | 7
50 | Structural work upto plinth beam | 2022-01-25 | 2022-02-04 | 8
51 | Structural work upto Ist Brace | 2022-02-07 | 2022-02-17 | 8
52 | Structural Work upto IInd Brace | 2022-02-18 | 2022-03-02 | 8
53 | Structural Work upto III rd Brace | 2022-03-03 | 2022-03-15 | 8
54 | Structural Work upto IVth Brace | 2022-03-16 | 2022-03-30 | 10
55 | Structural work upto floor slab | 2022-03-31 | 2022-04-19 | 13
56 | Structural work upto Roof slab | 2022-04-20 | 2022-05-30 | 28
57 | Supply and erection of columns pipes valves etc | 2022-04-22 | 2022-05-20 | 20
58 | Supply and erection of Flow meters | 2022-05-23 | 2022-05-30 | 5
59 | Testing and Commissioning | 2022-03-28 | 2022-04-04 | 5
60 | Finishing works | 2022-04-25 | 2022-06-06 | 30
61 | Construction of 5mld WTP | 2022-01-17 | 2022-11-03 | 290
62 | Aerator | 2022-01-18 | 2022-04-26 | 98
63 | Structural | 2022-01-18 | 2022-04-12 | 60
64 | Finishing | 2022-02-22 | 2022-04-26 | 45
65 | Flash Mixer including all structural and finishing works | 2022-01-18 | 2022-03-22 | 63
66 | Structural | 2022-01-18 | 2022-03-11 | 38
67 | Finishing | 2022-02-08 | 2022-03-22 | 30
68 | Clariflocculator | 2022-01-18 | 2022-09-21 | 246
69 | Providing inlet and scour pipe and upto base slab | 2022-01-18 | 2022-02-01 | 10
70 | RCC for outer wall of clarifier upto top | 2022-02-02 | 2022-04-27 | 60
71 | RCC for flocculator wall and central pier | 2022-04-28 | 2022-06-30 | 45
72 | RCC for collecting tray at intermediate level and walkway platorm at top | 2022-07-01 | 2022-07-22 | 15
73 | Plastering | 2022-07-25 | 2022-09-05 | 30
74 | Providing Handrail | 2022-09-06 | 2022-09-13 | 5
75 | Painting | 2022-09-14 | 2022-09-21 | 5
76 | Filter house including filter box, back wash trough, wash water tank, clear water channel and raw water channel, blower room, lobby etc. | 2022-01-17 | 2022-04-25 | 98
77 | Structural work of filter bed upto first floor | 2022-01-17 | 2022-04-25 | 70
78 | Brick work | 2022-04-26 | 2022-05-10 | 10
79 | Plastering | 2022-05-11 | 2022-05-25 | 10
80 | Flooring with tiles | 2022-05-11 | 2022-06-01 | 15
81 | Supplying and fixing wash water inlet pipes and laterals | 2022-04-27 | 2022-05-13 | 12
82 | Supplying & fitting grills, of window and door | 2022-05-18 | 2022-05-25 | 5
83 | Structural work including slab at second floor level | 2022-04-26 | 2022-06-28 | 45
84 | Brick work | 2022-06-29 | 2022-07-08 | 7
85 | Plastering | 2022-07-11 | 2022-07-21 | 8
86 | Flooring with tiles | 2022-07-22 | 2022-08-04 | 9
87 | Supplying and fitting grills of window and door | 2022-07-11 | 2022-07-15 | 4
88 | Supplying and laying filter media | 2022-08-05 | 2022-09-08 | 24
89 | Painting | 2022-07-22 | 2022-08-19 | 20
90 | Hand rail, MS ladder | 2022-07-22 | 2022-08-05 | 10
91 | Raw water channel structural | 2022-04-26 | 2022-05-10 | 10
92 | Raw water channel finishing | 2022-05-11 | 2022-05-23 | 8
93 | Chemical House including all structural and finishing works and providing chemical mixing tanks, stores etc. | 2022-04-26 | 2022-06-03 | 38
94 | Chemical house structural including mixing tank | 2022-04-26 | 2022-05-12 | 12
95 | Finishing | 2022-05-13 | 2022-06-03 | 15
96 | Clear water pump house and chlorine room including all structural and finishing works. | 2022-05-13 | 2022-06-22 | 40
97 | Structural | 2022-05-13 | 2022-05-31 | 12
98 | Finishing | 2022-06-01 | 2022-06-22 | 15
99 | Construction of Clear water sump including all structural and finishing works. | 2022-04-26 | 2022-06-03 | 38
100 | Structural | 2022-04-26 | 2022-05-12 | 12
101 | Finishing | 2022-05-13 | 2022-06-03 | 15
102 | Miscellaneous works including safety equipments, lab equipments, septic tank, water supply arrangements, sludge pit,road works and landscaping etc. Complete | 2022-09-22 | 2022-10-13 | 15
103 | Mechanical works including chlorinator, tonner, lifiting arrangements, weighing balance, floculating paddles, water level indicator, clarifier bridge, valves, pipes, gauges etc. | 2022-09-22 | 2022-11-03 | 30
104 | Electrical works including yard lighting, providing slow speed motors, blowers, panel board, internal and external wiring, lights and fans, lighting arrester etc. | 2022-09-22 | 2022-11-03 | 30
105 | Raw water pumping main | 2022-01-26 | 2022-06-20 | 145
106 | Supply of pipes | 2022-01-26 | 2022-03-09 | 30
107 | Laying of pipes | 2022-03-23 | 2022-06-15 | 60
108 | Testing and Commissioning | 2022-06-16 | 2022-06-20 | 2
109 | Clear water pumping mains | 2022-06-22 | 2022-12-07 | 168
110 | Supply of pipes | 2022-06-22 | 2022-08-03 | 30
111 | Laying of pipes | 2022-08-17 | 2022-11-16 | 65
112 | Testing and Commissioning | 2022-10-05 | 2022-12-07 | 45
113 | Supply and erection of Raw water pumpsets and Flow meters | 2023-03-29 | 2023-05-05 | 37
114 | Supply of pumpsets | 2023-03-29 | 2023-04-14 | 12
115 | Erection and energisation of pump sets | 2023-04-14 | 2023-05-05 | 15
116 | Supply of Flow meters | 2023-03-29 | 2023-04-14 | 12
117 | Installing Flow meters | 2023-04-28 | 2023-05-05 | 5
118 | Testing and Commissioning | 2022-06-16 | 2022-06-30 | 10
119 | Supply and erection of Clear water pumpsets and Flow meters | 2022-06-23 | 2022-08-26 | 64
120 | Supply of pumpsets | 2022-06-23 | 2022-08-04 | 30
121 | Erection and energisation of pump sets | 2022-08-05 | 2022-08-26 | 15
122 | Supply of Flow meters | 2022-06-23 | 2022-08-04 | 30
123 | Installing Flow meters | 2022-08-19 | 2022-08-26 | 5
124 | Testing and Commissioning | 2022-11-17 | 2022-12-01 | 10
125 | Distribution lines | 2022-01-27 | 2023-05-05 | 463
126 | Supply of DI Pipes phase 1 | 2022-01-27 | 2022-02-24 | 20
127 | Supply of DI Pipes phase 2 | 2022-02-25 | 2022-03-25 | 20
128 | Supply of DI Pipes phase 3 | 2022-03-28 | 2022-04-25 | 20
129 | Supply of DI Pipes phase 4 | 2022-04-26 | 2022-05-24 | 20
130 | Supply of DI Pipes phase 5 | 2022-05-25 | 2022-06-22 | 20
131 | Supply of PE pipes phase 1 | 2022-01-27 | 2022-02-24 | 20
132 | Supply of PE pipes phase 2 | 2022-02-25 | 2022-03-25 | 20
133 | Supply of PE pipes phase 3 | 2022-03-28 | 2022-04-25 | 20
134 | Supply of PE pipes phase 4 | 2022-04-26 | 2022-05-24 | 20
135 | Supply of PE pipes phase 5 | 2022-05-25 | 2022-06-22 | 20
136 | Supply of PE pipes phase 6 | 2022-06-23 | 2022-07-21 | 20
137 | Supply of PE pipes phase 7 | 2022-07-22 | 2022-08-19 | 20
138 | Laying and testing of DI Pipes phase 1 | 2022-02-10 | 2022-03-10 | 20
139 | Laying and testing of DI Pipes phase 2 | 2022-03-11 | 2022-04-08 | 20
140 | Laying and testing of DI Pipes phase 3 | 2022-04-11 | 2022-05-09 | 20
141 | Laying and testing of DI Pipes phase 4 | 2022-05-10 | 2022-06-07 | 20
142 | Laying and testing of DI Pipes phase 5 | 2022-06-08 | 2022-07-06 | 20
143 | Laying and testing of PE pipes phase 1 | 2022-02-10 | 2022-04-14 | 45
144 | Laying and testing of PE pipes phase 2 | 2022-04-15 | 2022-06-17 | 45
145 | Laying and testing of PE pipes phase 3 | 2022-06-20 | 2022-08-22 | 45
146 | Laying and testing of PE pipes phase 4 | 2022-08-23 | 2022-10-25 | 45
147 | Laying and testing of PE pipes phase 5 | 2022-10-26 | 2022-12-28 | 45
148 | Laying and testing of PE pipes phase 6 | 2022-12-29 | 2023-03-02 | 45
149 | Laying and testing of PE pipes phase 7 | 2023-03-03 | 2023-05-05 | 45
150 | Providing FHTCs | 2022-04-07 | 2023-06-22 | 315

## Sheet2
Aerator
Structural
Finishing
Flash Mixer including all structural and finishing works
Structural
Finishing
Clariflocculator
Providing inlet and scour pipe and upto base slab
RCC for outer wall of clarifier upto top
RCC for flocculator wall and central pier
RCC for collecting tray at intermediate level and walkway platorm at top
Plastering
Providing Handrail
Painting
Filter house including filter box, back wash trough, wash water tank, clear water channel and raw water channel, blower room, lobby etc.
Structural work of filter bed including slab at first floor level
Brick work
Plastering
Flooring with tiles
Supplying and fixing wash water inlet pipes and laterals
Supplying & fitting grills, of window and door
Supply of filter media
Structural work including slab at first floor level
Brick work
Plastering
Flooring with tiles
Supplying and fitting grills of window and door
Strutural work of wash water tank
Plastering
Painting
Hand rail, MS ladder
Raw water channel structural
Raw water channel finishing
Chemical House including all structural and finishing works and providing chemical mixing tanks, stores etc.
Chemical house structural including mixing tank
Finishing
Clear water pump house and chlorine room including all structural and finishing works.
Structural
Finishing
Construction of Clear water sump including all structural and finishing works.
Structural
Finishing
Miscellaneous works including safety equipments, lab equipments, septic tank, water supply arrangements, sludge pit,road works and landscaping etc. Complete
Mechanical works including chlorinator, tonner, lifiting arrangements, weighing balance, floculating paddles, water level indicator, clarifier bridge, valves, pipes, gauges etc.
Electrical works including yard lighting, providing slow speed motors, blowers, panel board, internal and external wiring, lights and fans, lighting arrester etc.