## Sheet1
TIME SCHEDULE FOR JJM - Parassala Panchyath -Design, Supplying, Laying Testing &commissioning of of 300 mm DI K9 From WTP site at Ponvilla to Idichakaplamoodu and Interconnection works(PERT)
Planned
|  | 18-25 Mar 22 | 25-30 Mar 22 | 1-5 April 22 | 5-10 April 22 | 10-15 April 22 | 15-18 April 22 | Actual
1 | supplying & laying distribution net work with 300mm DI K9
Activity | Laying pipe line with necessary joints
2 | supplying & laying distribution net work with 200mm DI K9
Activity | Laying pipe line with necessary joints
3 | Valve chamber and Interconnections
Activity | Construction of Vave chamber and related works
Interconnection with existing networks