## Sheet1
Name of work:-JJM-2020-21-WSS to Ayarkunnam Panchayath
Item No | Particulars | DAYS STARTING FROM 7-5-2021 to 6-2-2022
|  | May,2021 | June,2021 | July,2021 | Aug,2021 | Sept,2021 | Oct,2021 | Nov,2021 | Dec,2021 | Jan 2021& Feb 2021
1 | Road cutting permission from PWD/PMGSY
2 | Supply of pipe (MS/DI/PVC/GI)
3 | Supply and erection of Pump sets
4 | Construction of tranformer room
5 | Providing indoor type transformer
6 | Laying 250mm DI CWPM from WTP,Arumanoor to Elappani
7 | Laying distribution system in zone 2Elappani zone
8 | Laying distribution system in zone 1 Vazhepparambu Zone
9 | Providing FHTCs in Zone 1 &2