## Sheet1
WORK PLAN
JJM 2021-22 - Providing balance FHTC, distribution network and construction of 7LL OHSR in Velinalloor Panchayath in Kollam District
YEAR | SCHEDULE | [8 empty] | 2023
MONTH |  | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY
SUPPLY OF MATERIALS | PLANNED
LAYING OF 200mm DI K9 CWPM | PLANNED
CONSTRUCTION OF 7LL OHSR - RCC WORK UPTO FLOOR SLAB LEVEL | PLANNED
CONSTRUCTION OF 7LL OHSR - RCC WORK COMPLETION | PLANNED
CONSTRUCTION OF 7LL OHSR - FINISHING WORK | PLANNED
PROVIDING 5732 FHTCs | PLANNED
LAYING OF DISTRIBUTION NETWORK | PLANNED
OVER ALL PROGRESS | PLANNED