## Sheet1
COMPONENTS |  | START DATE | DAYS TO COMPLETE | remarks
Agreement executed |  | 2021-01-08 | 15
15
5
supply of materials |  | 2021-03-12 | 15
20
10
FHTCs work started for inauguration |  | 2021-02-20 | 1
10
30
Survey work |  | 2021-02-21 | 18
93
45
FHTCs work |  | 2021-02-20 | 580
30
21
laying work |  | 2021-03-12 | 550
65
49
BPT at Thannithadam |  | 2022-01-01 | 320
line testing and third party inspection |  | 2021-04-01 | 520
30
30
Supply and fixing of valves, Construction of chambers,etc |  | 2021-05-16 | 90
30
20
Commissioning and Other Miscellaneous Activities |  | 2022-11-15 | 15
15
SCOPE | 200 KM laying + 8088 FHTC
Completed as on 20.12.2021 | 25.4 KM Laying + 817 FHTC
JJM-ACTION PLAN FOR PROVIDING 8802 FHTCs in VELIYAM Pt
Sl.No | Item of work | 2021-02-01 |  |  |  | 2021-03-01 |  |  |  | 2021-04-01 |  |  |  | 2021-05-01 |  |  |  | 2021-06-01 |  |  |  | 2021-07-01 |  |  |  | 2021-08-01 |  |  |  | 2021-09-01 |  |  |  | 2021-10-01 |  |  |  | 2021-11-01 |  |  |  | 2021-12-01 |  |  |  | 2022-01-01 |  |  |  | 2022-02-01 |  |  |  | 2022-03-01 |  |  |  | 2022-04-01 |  |  |  | 2022-05-01 |  |  |  | 2022-06-01 |  |  |  | 2022-07-01 |  |  |  | 2022-08-01 |  |  |  | 2022-09-01 |  |  |  | 2022-10-01 |  |  |  | 2022-11-01 |  |  |  | 2022-12-01
|  | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4
1 | LINE EXTENSION WORKS | 2021-05-01 Week 1: 25.40 km laid; 2021-12-01 Week 3: Balance laying- 56 km
2 | Planned FEASIBLE HOUSE CONNECTION (8088 FHTCs) |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 88
3 | Actual Progress | 2021-02-01 Week-4: 817 FTHCs completed
4 | Rescheduled- FHTCS | 2021-12-01 Week-4: 150; 2022-01-01 Week 1: 150; 2022-01-01 Week 2: 150; 2022-01-01 Week 3: 150; 2022-01-01 Week-4: 150; 2022-02-01 Week 1: 150; 2022-02-01 Week 2: 150; 2022-02-01 Week 3: 150; 2022-02-01 Week-4: 150; 2022-03-01 Week 1: 150; 2022-03-01 Week 2: 150; 2022-03-01 Week 3: 150; 2022-03-01 Week-4: 150; 2022-04-01 Week 1: 150; 2022-04-01 Week 2: 150; 2022-04-01 Week 3: 150; 2022-04-01 Week-4: 150; 2022-05-01 Week 1: 150; 2022-05-01 Week 2: 150; 2022-05-01 Week 3: 150; 2022-05-01 Week-4: 150; 2022-06-01 Week 1: 150; 2022-06-01 Week 2: 150; 2022-06-01 Week 3: 150; 2022-06-01 Week-4: 150; 2022-07-01 Week 1: 150; 2022-07-01 Week 2: 150; 2022-07-01 Week 3: 150; 2022-07-01 Week-4: 150; 2022-08-01 Week 1: 150; 2022-08-01 Week 2: 150; 2022-08-01 Week 3: 150; 2022-08-01 Week-4: 150; 2022-09-01 Week 1: 150; 2022-09-01 Week 2: 150; 2022-09-01 Week 3: 150; 2022-09-01 Week-4: 150; 2022-10-01 Week 1: 150; 2022-10-01 Week 2: 150; 2022-10-01 Week 3: 150; 2022-10-01 Week-4: 150; 2022-11-01 Week 1: 150; 2022-11-01 Week 2: 150; 2022-11-01 Week 3: 150; 2022-11-01 Week-4: 150; 2022-12-01 Week 1: 150; 2022-12-01 Week 2: 130; 2022-12-01 Week 3: 130; 2022-12-01 Week-4: 111
148.3878