## Sheet1
WORK SCHEDULE
Name of Work: JJM-Kannur District- WSS to Cheruvanchery village in Pattiam panchayath- Phase I- Construction of service reservoirs and laying distribution network and providing FHTCs.
Date | Progress in % | Details of work
13.09.2022 | 0 | Agreement execution
13.10.2022 | 5 | Placing order to pipes, Tank work
13.11.2022 | 20 | Supply of pipes,Tank work and earth work excavation and Pipe laying
24.12.2022 | 35 | Pipe laying, Tank work and providing HTCs
24.01.2023 | 45 | Pipe laying, Tank work and providing HTCs
24.02.2023 | 60 | Pipe laying, Tank work and providing HTCs
24.03.2023 | 75 | Pipe laying, Tank work and providing HTCs
24.04.2023 | 90 | Pipe laying, and providing FHTCs
24.05.2023 | 100 | Pipe laying, and providing FHTCs and commissioning the scheme

## Sheet2
WORK SCHEDULE
JJM - Kannur District- Chembilode Panchayath - WSS to Anjarakandy, Peralassery and adjoining Panchayaths Phase II
Date | Progress in % | Details of work
2020-11-05 | 0 | Work order
2020-12-05 | 7 | Supplying pipes, specials and Valves
2021-01-15 | 15 | Providing Water connection
2021-02-15 | 60 | Earth work and Pipe laying
2021-03-15 | 60 | Earth work and Pipe laying
2021-04-15 | 70 | Earth work and Pipe laying
2021-05-15 | 70 | Earth work and Pipe laying
2021-06-15 | 70 | Earth work and Pipe laying