## Sheet1
“KIIFB – Tranche 12.WRD 025-35(2017-18)-Chathannoor Drinking water project –Extension of Distribution system from JICA scheme in various villages under Chathanoor constituency -Paravoor Municipality(Package I)
COMPONENTS | START DATE | DAYS TO COMPLETE
Restart | 2021-09-15 | 1
supply of pipes ( III lot) | 2021-09-28 | 15
Laying , Conveying and compaction | 2021-10-11 | 70
Supply & fixing of valves | 2021-12-01 | 8
Construction of Valve chambers | 2021-12-02 | 18
PCC - road restoration works | 2021-11-03 | 45
Commissioning & trail running | 2021-12-25 | 5
“KIIFB – Tranche 12.WRD 025-35(2017-18)-Chathannoor Drinking water project –Extension of Distribution system from JICA scheme in various villages under Chathanoor constituency -Poothakulam(Package VI)
COMPONENTS | START DATE | DAYS TO COMPLETE
Restart | 2021-09-15 | 1
supply of pipes ( III lot) | 2021-09-28 | 15
Laying , Conveying and compaction | 2021-10-11 | 100
Supply & fixing of valves | 2021-12-01 | 18
Construction of Valve chambers | 2021-12-02 | 30
PCC - road restoration works | 2021-11-03 | 53
Commissioning & trail running | 2022-01-25 | 5