## pipe laying
PIPE LAYING AT KOTTAMKARA PANCHAYATH 2022-23
Sl.No. | Duration | Pipe laying(Km)
1 | June | 6
2 | July | 9
3 | Aug. | 9
4 | Sep. | 9
5 | Oct. | 9
6 | Nov | 9
7 | Dec | 9
8 | Jan | 9
9 | Feb | 9
10 | Mar | 9
11 | Apr | 9
12 | May | 9
13 | June | 9
14 | July | 8.468
122.468

## OHSR
OHSR AT KOTTAMKARA
Sl.No. | Activity | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July(24 month )
1 | Agreement executed | bar: Mar
2 | Site survey,finalisation and approval of design drawing | bar: Apr to Jun
3 | Demolishing the existing dispensary building partialy/completely | bar: July to Aug
4 | Construction of 10LL OHSR at Mekkone near Ayurveda hospital | bar: Aug to Mar
5 | Construction of 3LL OHSR at Mampuzha | bar: Sep to Mar
6 | Renovation existing OHSR at Mampuzha | bar: Feb to Apr
7 | Construction of Valve chamber | bar: Mar to May
8 | Construction of Building under tank(Electrical,Plumping etc.) | bar: Mar to Jun
9 | Defect liability period and operation and maintanance period