## Sheet1
JJM- Kannur District - Pattiam Panchayat - WSS to Kuthuparamba Municipality, Kottayam and Pattiam Panchayaths - Phase II
Date | Progress | Details of work
2020-11-02 | 1 | Project Start
2020-11-09 | 2 | Tender Process
2020-11-11 | 3 | Tender Approval
2021-01-04 | 4 | Agreement
2021-01-05 | 5 | Site Hand over
2021-01-08 | 15 | Supply of Pipes and specials
2021-04-08 | 75 | Earth Work and pipe laying
2021-04-14 | 90 | PWD road restoration work
2021-04-20 | 95 | Trail run and commisioning
2021-04-30 | 100 | Bill payment