## Sheet1
COMPONENTS |  | START DATE | DAYS TO COMPLETE | remarks
Agreement executed |  | 2021-02-10 | 24
24
5
supply of materials |  | 2021-04-19 | 10
13
10
FHTCs work started for inauguration |  | 2021-02-20 | 1
10
30
Survey work |  | 2021-02-21 | 18
93
45
FHTCs work |  | 2021-02-20 | 250 | Retrofitting connection completed
30
21
laying work |  | 2021-03-21 | 400 | delayed due to cutting sanction delay
65
49
line testing and third party inspection |  | 2022-04-01 | 400
30
30
Supply and fixing of valves, Construction of chambers,etc |  | 2022-05-31 | 90
30
20
Commissioning and Other Miscellaneous Activities |  | 2022-09-15 | 15
SCOPE | 94.4 KM laying + 8802 FHTC
Completed as on 01.6.2021 | 63 KM Laying + 2200 FHTC
JJM-ACTION PLAN FOR PROVIDING 8802 FHTCs in VELIYAM Pt
Sl.No | Item of work | 2021-02-01 |  |  |  | 2021-03-01 |  |  |  | 2021-04-01 |  |  |  | 2021-05-01 |  |  |  | 2021-06-01 |  |  |  | 2021-07-01 |  |  |  | 2021-08-01 |  |  |  | 2021-09-01 |  |  |  | 2021-10-01 |  |  |  | 2021-11-01 |  |  |  | 2021-12-01 |  |  |  | 2022-01-01 |  |  |  | 2022-02-01 |  |  |  | 2022-03-01 |  |  |  | 2022-04-01 |  |  |  | 2022-05-01 |  |  |  | 2022-06-01 |  |  |  | 2022-07-01 |  |  |  | 2022-08-01 |  |  |  | 2022-09-01
|  | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 1 | Week 2 | Week 3 | Week-4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20
1 | LINE EXTENSION WORKS | 2021-02-01 Week 1: 63 km laid; 2022-06-01 Week 5: 20 KM
2 | Planned FEASIBLE HOUSE CONNECTION (8802 FHTCs) |  | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 62 | 60 | 60 | 60
3 | Actual Progress | 2021-02-01 Week-4: 2100 FTHCs completed
4 | Rescheduled- FHTCS | 2021-02-01 Week 1: 2200 FHTCs; 2022-06-01 Week 5: 112; 2022-06-01 Week 6: 112; 2022-06-01 Week 7: 112; 2022-06-01 Week 8: 112; 2022-07-01 Week 9: 112; 2022-07-01 Week 10: 112; 2022-07-01 Week 11: 112; 2022-07-01 Week 12: 112; 2022-08-01 Week 13: 112; 2022-08-01 Week 14: 112; 2022-08-01 Week 15: 112; 2022-08-01 Week 16: 112; 2022-09-01 Week 17: 112; 2022-09-01 Week 18: 112; 2022-09-01 Week 19: 112; 2022-09-01 Week 20: 112
maximum 4000 FHTCs are only possible from current pipelines