## Sheet1
WORK PLAN
BAWSS to Kundara and adjoining Panchayaths-Replacement of old 500 mm AC transmission main with 500 mm DI pipe from Padinjaretheruvu to Pulamon Jn
Components | Start date | Days to complete
Estimate approval, Tendering, Agreement execution | 2021-07-21 | 30 days
PIPE LAYING | 2022-05-04 | 30 days