## Sheet3
2020
|  | 2020 |  | 2020 | [11 empty] | 2021
PLANNED Vs ACTUAL PROGRESS
Jal Jeevan Mission -Phase I-BAWSS to Kundara and adjoining panchayaths- Providing house connection from existing pipe line, extension of pipe line and Replacement of pipe line and part of rennovation work in WTP(Elampal) in Kundara grama panchayath
Year | SCHEDULE |  |  | 2020 | [11 empty] | 2021 | [12 empty] | 2022
Month |  |  |  | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG |  | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG |  | SEP | OCT | NOV | DEC
Estimate approval,tendering,agreement execution | Planned
| Actual | [22 empty] | 35 % completed | [12 empty] | 35 % completed
Supplay of pipe and specials | Planned
Actual
FHTC Implementation | Planned | bar: SEP to 2022 JAN
Actual
pipe replacement and pipeline extension | Planned | bar: SEP to 2022 JAN
Actual
rennovation work in WTP(Elampal) | Planned | bar: SEP to 2022 JAN
| Actual | [18 empty] | Not yet started
Overall progress | [19 empty] | 26% completed