## Sheet1
KIIFB-Project-11-Replacing 350 mm dia AC pipe of distribution main of zone II-Kolecheery WSS with DI pipes from Vaduvankulam to Panayathamparamba Break pressure tank for enhancement of coverage in Kuttiattoor, Koodali, Munderi and Keezhallur panchayaths
Date | Progress | Details of work
18.01.2019 | 1 | Project Start
15.04.2021 | 2 | Tender Process
31.05.2021 | 3 | Tender Approval
05.06.2021 | 4 | Agreement
05.06.2021 | 5 | Site Hand over
20.11.2021 | 15 | Supply of Pipes and specials
25.08.2022 | 75 | Earth Work and pipe laying
15.09.2022 | 90 | PWD road restoration work
20.09.2022 | 95 | Trail run and commisioning
28.09.2022 | 100 | Bill payment