## Schedule for completion
NRDWP:WSS to Vakathanam Panchayath: 12 m dia well at peroor - Tentative work shedule of balance work
Sl No: | Item of work | Details | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01
1 | Civil work | Works for handrail,Window shutter,rolling shutter,ventilators,painting,gate fitting,valve chamber
2 | Mechnical work | 10 Ton Gantry crane
3 | Leading pipe and connected works
4 | Retaining wall/Compound wall
5 | Construction of road
6 | Earth filling and landscaping